## Sheet1
MINISTRY OF WORK AND TRANSPORT, 2018 FISCAL YEAR
PROCUREMENT PLAN FOR THE YEAR 2018
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
| Procuring Entry Name | Ministry of Work And Transport, 2018 Fiscal Year
2 | A: Procurement Plan for the Year; B: 2018
3 | A: Version
4 | A: Date Last Updated
5 | A: Comment
6
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenses At:(Provided Dates) | Actual Expenditure Amount | Balance At: (Provided Dates) | Balance Amount | Comment
1 | Works | 72141000 | Construction of Umuobo Obuna Ihuenu – Ring road. | EBS/SCPP/LOA/II/336 | 34001001/ 23020118/ 17000055 | - | - | 2200000000 | Budgetary provision | Yes | Open Competitive Tendering | 2018-07-09 | 2018-08-20 | 2018-09-13 | 12 Months | - | 2018 | 2656725997.8 | NIL | NIL | Completed
2 | Works | 72141000 | Construction of 490 concrete lined drain and cell box culvert at Industrial unit | EBS/SCPP/LOA/II/337 | 34001001/ 23020118/ 17000075 | - | - | 93488375.26 | Budgetary provision | Yes | Open Competitive Tendering | 2018-07-09 | 2018-08-20 | 2018-09-10 | 12 Months | 93488375.26 | 2018 | 146511460.7 | NIL | NIL | Completed
3 | Works | 72141000 | Construction of GTC Agba – Agbaelu Egu – Enu – Isu (10.3km) | EBS/SCPP/LOA/II/360 | 34001001/ 23020118/ 17000033 | 10.34KM | 10.3KM | 300000000 | Budgetary provision | Yes | Open Competitive Tendering | 2018-09-28 | 2018-11-09 | 2018-11-30 | 12 Months | 300000000 | 2018 | 1323601294.57 | NIL | NIL | Completed
4 | Works | 72141000 | Construction of Okofia internal roads in Ezza South L.G.A (5KM) | EBS/SCPP/LOA/II/359 | 34001001/ 23020118/ 17000058 | 5KM | 5KM | 736377276 | Budgetary provision | Yes | Open Competitive Tendering | 2018-09-28 | 2018-11-09 | 2018-11-25 | 12 Months | - | 2018 | 690680637.15 | NIL | NIL | Completed
5 | Works | 72141000 | Construction of a section of Umuoghara Achiagu road (1.6km) | EBS/SCPP/LOA/II/361 | 34001001/ 23020118/ 17000056 | 1.6KM | 1.6KM | 1928293489.46 | Budgetary provision | Yes | Selective Tendering | 2018-09-28 | 2018-11-09 | 2018-11-28 | 12 Months | - | 2018 | 209318213.97 | NIL | NIL | Completed
6 | Works | 72141000 | Approval for the cost of total works for the construction of Abandoned section of Abakaliki Afikpo road (14.5km) | EBS/SCPP/LOA/II/230B | 34001001/ 23020118/ 17000115 | 14.5KM | 14.5KM | 250000000 | Budgetary provision | Yes | Selective Tendering | 2018-01-10 | 2018-02-26 | 2018-03-19 | 12 Months | 250000000 | 2018 | 2344311314.36 | NIL | NIL | Completed
7 | Works | 72141000 | Construction of flyover bridge Abomege | EBS/SCPP/LOA/II/347 | 34001001/ 23020118/ 17000080 | - | - | 1000000000 | Budgetary provision | Yes | Selective Tendering | 2018-08-14 | 2018-10-18 | 2018-11-10 | 12 Months | - | 2018 | 1368500000 | NIL | NIL | Completed
8 | Works | 72141000 | Construction of Onuigboji Junction to Nwa – Noyo stadium (5.8km) | EBS/SCPP/LOA/II/348 | 34001001/ 23020118/ 17000018 | 5.8KM | 5.8KM | 1704757 | Budgetary provision | Yes | Selective Tendering | 2018-08-14 | 2018-10-18 | 2018-11-10 | 12 Months | 1704757 | 2018 | 909010756.5 | NIL | NIL | Completed
9 | Works | 72141000 | Construction of Uburu Akaeze Road | EBS/SCPP/LOA/II/349 | 34001001/ 23020118/ 17000046 | - | - | 1000000000 | Budgetary provision | Yes | Selective Tendering | 2018-08-14 | 2018-10-18 | 2018-11-13 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
10 | Works | 72141000 | Construction of concrete lined drain at Abakaliki fertilizer plan | EBS/SCPP/LOA/II/321 | 34001001/ 23020118/ 17000074 | - | - | 82502876.28 | Budgetary provision | Yes | Selective Tendering | 2018-05-01 | 2018-07-13 | 2018-08-03 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
11 | Works | 72141000 | Approval for the revised sum due to some additional works on the construction of Handrails at Presco junction flyover bridge fountain and surrounding | EBS/SCPP/LOA/II/331 | 34001001/ 23020118/ 17000092 |  |  | 20984888 | Budgetary provision | Yes | Selective Tendering | 2018-06-25 | 2018-08-16 | 2018-09-07 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
12 | Works | 24111810 | Approval for the revised contract sum on the construction of Ugwu Achara Water Reservoir road | EBS/SCPP/LOA/II/343 | 34001001/ 23020118/ 17000108 | 6.9KM |  | 320000000 | Budgetary provision | Yes | Selective Tendering |  | 2018-08-20 | 2018-09-10 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
13 | Works | 72141000 | Approval for the revised contract sum due to some additional works on the construction of Ndiagu Layout internal Road in Abakaliki | EBS/SCPP/LOA/II/342 | 34001001/ 23020118/ 17000106 | 6.6KM |  | 400000000 | Budgetary provision | Yes | Selective Tendering | 2018-06-28 | 2018-09-20 | 2018-09-12 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
14 | Works | 72141000 | Approval for the revised contract sum due to additional works on the construction of flyover bridge at international market | EBS/SCPP/LOA/II/230C | 34001001/ 23020118/ 17000093 |  |  | 631177101.5 | Budgetary provision | Yes | Selective Tendering | 2018-03-20 | 2018-05-28 | 2018-06-26 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
15 | Works | 72141000 | Approval for the revised of bill of Engineering measurement and evaluation (BEME)for the Asphalting of schools of Nursing premises Uburu. | EBS/SCPP/LOA/II/231 |  |  |  | 350000000 | Budgetary provision | Yes | Selective Tendering | 2018-01-08 | 2018-03-05 | 2018-04-28 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
16 | Works | 72141000 | Construction of Ebonyi voice junction mile 50 layout internal Road Abakaliki (1.4km) | EBS/SCPP/LOA/II/233 |  |  |  |  | Budgetary provision | Yes | Open Competitive Tendering | 2018-01-29 | 2018-03-26 | 2018-04-25 | 12 Months | 100000000 | 2018 | 2227197768.8 | NIL | NIL | Completed
17 | Works | 72141000 | Revised contract sum to accommodate additional (5km) for the construction of Ishieke Odomoke road (20km) | EBS/SCPP/LOA/II/225 | 34001001/ 23020118/ 17000001 | 1.4KM |  | 1200000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-10-30 | 2018-11-26 | 2018-12-16 | 12 Months | 1200000000 | 2018 | 3238216492.46 | NIL | NIL | Completed
18 | Works | 72141000 | Approval for the revised contract sum due to increased in the scope of works on the construction of Handrails at international market flyover bridge fountain and surroundings. | EBS/SCPP/LOA/II/334 | 34001001/ 23020118/ 17000096 | 25KM |  | 11304887 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-08-16 | 2018-09-16 | 2018-10-07 | 12 Months | 11304886.88 | 2018 | 23980129.2 | NIL | NIL | Completed
19 | Works | 72141000 | Contract for the construction of President Muhammadu Buhari Overhead Bridge. | EBS/SCPP/LOA/II/229 | 34001001/ 23020118/ 17000070 |  |  | 961317415.06 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-01-02 | 2018-01-08 | 2018-01-29 | 12 Months | 961317415.06 | 2018 | 1168332949.72 | NIL | NIL | Completed
20 | Works | 72141000 | Construction of Ezzamgbo Road (20km) to accommodate additional (5KM) | EBS/SCPP/LOA/II/ | 34001001/ 23020118/ 17000015 | 25KM |  | 740285312.5 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-06 | 2018-11-26 | 2018-12-18 | 12 Months | 740285312.5 | 2018 | 3493557461.95 | NIL | NIL | Completed
21 | Works | 72141000 | Construction of Ntezi- Agba Isu Road (15km) Isielu L.G.A | EBS/SCPP/LOA/II/371 | 34001001/ 23020118/ 17000012 | 15km | 15km | 2000000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-16 | 12 Months | 2000000000 | 2018 | 2245844764.28 | NIL | NIL | Completed
22 | Works | 72141000 | Construction of Sharon- Iboko road (7.3km) in Izzi L.G.A | EBS/SCPP/LOA/II/372 | 34001001/ 23020118/ 17000061 | 15km | 15km | 1000000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-17 | 12 Months | 0 | 2018 | 1364253103.24 | NIL | NIL | Completed
23 | Works | 72141000 | Construction of Oferekpe Obvudechi Oyege Nduofutu road Izza L.G.A | EBS/SCPP/LOA/II/373 | 34001001/ 23020118/ 17000057 | 9.3km | 9.5km | 300000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-17 | 12 Months | 0 | 2018 | 1020577302.65 | NIL | NIL | Completed
24 | Works | 72141000 | Construction of Afikpo North Dualization from Amasiri Junction to Uwana round about (3.52km) | EBS/SCPP/LOA/II/377 | 34001001/ 23020118/ 17000062 | 3.52 | 3.52km | 100000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-17 | 12 Months | 0 | 2018 | 1173191267.78 | NIL | NIL | Completed
25 | Works | 72141000 | Construction of Ukwuachi Oshegbe road project in Ezza North L.G.A (11.2km) | EBS/SCPP/LOA/II/378 | 34001001/ 23020118/ 17000006 | 11.2km | 11.2km | 1200000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-17 | 12 Months | 1200000000 | 2018 | 1619960731.21 | NIL | NIL | Completed
26 | Works | 72141000 | Award of contract for the construction of Mile 50 Ishieke road project from Ugwu Achara Junction to Enugu Highway (7.265km) in the Capital City | EBS/SCPP/LOA/II/374 | 34001001/ 23020118/ 17000060 |  | 7.26km | 300000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-18 | 12 Months | 0 | 2018 | 1858256851.19 | NIL | NIL | Completed
27 | Works | 72141000 | Award of contract for the construction of Ojon Nwida road project (5km) in Ikwo L.G.A | EBS/SCPP/LOA/II/375 | 34001001/ 23020118/ 17000005 | 5km | 5km | 743000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-11-01 | 2018-12-26 | 2019-01-18 | 12 Months | 743000000 | 2018 | 687118998.8 | NIL | NIL | Completed
28 | Works | 72141000 | Award of contract for the construction of the Obujia- nwanwu road project in Abakaliki L.G.A | EBS/SCPP/LOA/II/376 | 34001001/ 23020118/ 17000039 | 9.5km | 9.5km | 500000000 | Budgetary Provision | Yes | Selective Tendering | 2018-11-01 | 2018-12-26 | 2019-01-18 | 12 Months | 0 | 2018 | 1295744531.22 | NIL | NIL | Completed
29 | Works | 72141000 | Revised contract sum due to some additional works on the rehabilitation of Auro-Eke market round-about Ngodo - St. Mary Amangbala-Amaizu-Ndibe-Amankwo with a spur of 1.3km to Iduigariwey Road | EBS/SCPP/LOA/II/311 | 34001001/ 23020118/ 17000004 |  | 1.3km | 600000000 | Budgetary Provision | Yes | Selective Tendering | 2018-04-23 | 2018-06-22 | 2018-07-12 | 12 Months | 600000000 | 2018 | 888099889.04 | NIL | NIL | Completed
30 | Works | 72141000 | Revised contract sum of due to some additional works on the constructin of Kpirikpiri Junction, St. Patrick - Unity FM road and Osborn Lapalm, Otozi - Stephen Mgbabor - Ezeokwo Street in Abakaliki | EBS/SCPP/LOA/II/341 | 34001001/ 23020118/ 17000109 | 1.3km | 5.64km | 330000000 | Budgetary Provision | Yes | Selective Tendering | 2018-06-18 | 2018-08-20 | 2018-09-10 | 12 Months | 330000000 | 2018 | 704086118.4 | NIL | NIL | Completed
31 | Works | 72141000 | Revised contract sum on the construction of Chief Stephen Omege-Watchman, Dr.John Eke, Chukwuma Ofoke, Ogodo Osike-Uro Cresent-Ajiagbu Ugo Martins-Owa-Okoro Nwokoro- Awcuzu-Igu-Streets in Abakaliki | EBS/SCPP/LOA/II/131 |  |  | 8.41km | 325000000 | Budgetary Provision | Yes | Selective Tendering | 2018-06-18 | 2018-08-20 | 2018-09-10 | 12 Months | 5325000000 | 2018 | 892393599.43 | NIL | NIL | Completed
32 | Works | 72141000 | Approval for the revised contract sum on the construction of Golf quary Express Road-Ezza Road, Emefor Umune Emefor Nnorom-Ezeadikwa-Ugo Dan/Agbaja Road and off Hatchery Road (Streets in zone 6 Abakaliki). | EBS/SCPP/LOA/II/340 |  |  | 7.09km | 450,000,000.00 | Budgetary Provision | Yes | Selective Tendering | 2018-06-20 |  | 2018-09-10 | 12 Months | 450000000 | 2018 | 712111260 | NIL | NIL | Completed
33 | Works | 72141000 | Reconstruction of Internal Road of Nkwwegu cantonment, Abakaliki. | EBS/SCPP/LOA/II/221 |  |  | 5km | 600,000,000.00 | Budgetary Provision | Yes | Selective Tendering | 2017-09-12 | 2018-01-08 | 2018-01-30 | 12 Months | 600000000 | 2018 | 562510834.2 | NIL | NIL | Completed
34 | Works | 72141000 | Construction of Rein forced conctrete Bridge along ogwor-okue Nzerem Road | EBS/SCPP/LOA/II/222 |  |  | 11.2km | 100,000,000.00 | Budgetary Provision | Yes | Selective Tendering | 2017-09-12 | 2018-01-08 | 2018-01-30 | 12 Months | 956348260 | 2018 | 464664461.87 | NIL | NIL | Completed
35 | Works | 72141000 | Consrtuction of 4 span Rein forced concrete Bridge along Amaogwu Uburu Akaeze Road. | EBS/SCPP/LOA/II/223 |  |  |  | 20,000,000.00 | Budgetary Provision | Yes | Selective Tendering | 2017-12-12 | 2018-01-08 | 2018-01-30 | 12 Months | 400000000 | 2018 | 394556927.86 | NIL | NIL | Completed
36 | Works | 72141000 | Contract for the Resultation of Abakaliki Enugu Road | EBS/SCPP/LOA/II/224 |  |  |  | 100,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 2017-12-12 | 2018-01-08 | 2018-01-30 | 12 Months | - | 2018 | 685651618.89 | NIL | NIL | Completed
37 | Works | 72141000 | Construction of 2No span Reinforced concrete Bridge at Ishieke odomke | EBS/SCPP/LOA/II/225 |  |  |  | 500,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 16/12/2017 | 2018-01-08 | 2018-01-30 | 12 Months | 500000000 | 2018 | 426189277.94 | NIL | NIL | Completed
38 | Works | 72141000 | Contract for the Aforezunna, Amike and Ojebogene strret (1.3km). | EBS/SCPP/LOA/II/226 |  |  | 1.3km | 200,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 16/12/2017 | 2018-01-08 | 2018-01-30 | 12 Months | 200000000 | 2018 | 171,888,154,.01 | NIL | NIL | Completed
39 | Works | 72141000 | Construction of umuobo, Oboma, Iheenu Ring Road (15km) | EBS/SCPP/LOA/II/227 |  |  | 15km | 2,200,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 17/12/2017 | 2018-01-08 | 2018-01-30 | 12 Months | - | 2018 | 2350838160 | NIL | NIL | Completed
40 | Works | 72141000 | Contract for the construction/Extension of 3span, 2span and 4 No: 1 span Bridges along Nkwegu Ehamufu Road | EBS/SCPP/LOA/II/228 |  |  |  | 840,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 17/12/2017 | 2018-01-08 | 2018-01-30 | 12 Months | 840000000 | 2018 | 867585076 | NIL | NIL | Completed
41 | Works | 72141000 | Contract for the construction of Bypass Glass tunnel with retaining usual from Aforezuna to Abakaliki Junction | EBS/SCPP/LOA/II/230 | 34001001 /2302011 8/170000 27 | 15km | 1km | 1,000,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 17/12/2017 | 2018-01-08 | 2018-01-30 | 12 Months | 1000000000 | 2018 | 956929342.95 | NIL | NIL | Completed
42 | Works | 72141000 | Approval for the revised contract sum Bill of Engineering measurement and Evaluation (BEME) for the construction of flyover bridge at International Market Ancillary work (Lot II) project | EBS/SCPP/LOA/II/230C | 34001001/ 23020118/ 17000082 | 1KM |  | 631,177,101.50 | Budgetary Provision | Yes | Open Competitive Tendering | 24/10/2018 | 22/1/2018 | 2018-02-12 | 12 Months | 631177101.5 | 2018 | 773137628.26 | NIL | NIL | Completed
43 | Works | 72141000 | Construction of Federal Road Safety Commission road to Abakaliki | EBS/SCPP/LOA/II/328 | 34001001/ 23020118/ 17000119 | - |  | 27,544,801.70 | Budgetary Provision | Yes | Open Competitive Tendering | 14/5/2018 | 13/7/2018 | 2018-08-05 | 12 Months | 27544801.7 | 2018 | 54487686.14 | NIL | NIL | Completed
44 | Works | 72141000 | Approval for the revised contract sum on construction of Umueze Ecckankar – Enugu Expressway mbam Agbo – Phase and 2 – Presco Junction street Luke Church Okposi Umuoghara with spur to haraca in zone 7 Abakaliki1 | EBS/SCPP/LOA/II/335 | 34001001/ 23020118/ 17000107 | - | 6.77km | 350,000,000.00 | Budgetary Provision | Yes | Open Competitive Tendering | 17/8/2018 | 23/12/2018 | 2018-08-31 | 12 Months | 350000000 | 2018 | 731339391.3 | NIL | NIL | Completed
45 | Works | 72141000 | Approval for the revised contract sum on the rehabilitation of fourteen streets within Abakaliki Capital City | EBS/SCPP/LOA/II/338 | 34001001/ 23020118/ 17000106 | 6.77KM | 5.76km | 342,186,076.30 | Budgetary Provision | Yes | Selective Tendering | 2018-06-08 | 20/8/2018 | 2018-09-10 | 12 Months | 342186076.3 | 2018 | 338508246.18 | NIL | NIL | Completed
46 | Works | 72141000 | Approval for the revised contract sum due to some additional works on the construction of President Muhammed Buhari overhead bridge project | EBS/SCPP/LOA/III/354 | 34001001/ 23020118/ 17000070 | 5.76KM |  | 961,317,415.06 | Budgetary Provision | Yes | Selective Tendering | 17/9/2018 | 18/10/2018 | 9/11/2018 | 12 Months | 96,1317,415.06 | 2018 | 2827143087.72 | NIL | NIL | Completed
47 | Works | 72141000 | Approval for the revised contract sum due to some additional works on the construction of A section of Umuoghara Achar Achiagu road project in Ezza North L.G.A to include additional (5.82km) from CHO + 000 to CH5+820 making a total of 17.52km | EBS/SCPP/LOA/III/363 | 34001001/ 23020118/ 17000056 |  | 17.52km | 1928293489.64 | Budgetary Provision | Yes | Selective Tendering | 2018-08-10 | 9/11/2018 | 30/11/2018 | 12 Months | 0 | 2018 | 1707340235.26 | NIL | NIL | Completed