## Sheet1
MINISTRY OF HEALTH, 2018 FISCAL YEAR
PROCUREMENT PLAN FOR THE YEAR 2018
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
1 | A: Procuring Entry Name; B: Ministry of Health, 2018 Fiscal Year
2 | A: Procurement Plan for the Year; B: 2018
3 | A: Version
4 | A: Date Last Updated
5 | A: Comment
6
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenses At:(Provided Dates) | Actual Expenditure Amount | Balance At: (Provided Dates) | Balance Amount | Comment
1 | Works | 7044 | Award of contract for the Perimeter fencing of Onueke General Hospital | EBS/SCPP/LOA/III/362 | 21001001/ 23020106/ 04000004 |  | - | - | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-11-09 | 2018-11-30 | Completed | 48225230.5 | 2018 | 84172920.48 | NIL | NIL | Completed
2 | Works | 7044 | Construction Of Perimeter Fencing And Gate House At Ebonyi State College of Nursing and Mid-Wifery Uburu | EBS/SCPP/LOA/II/256 | 21001001/ 23020122/ 4000016 |  | - | - | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-04-19 | 2018-05-09 | Completed | 82059526.14 |  | 99553783.83 | NIL | NIL | Completed
3 | Works | 7044 | Approval for revised contract sum due to some additional works on the landscaping of General Hospital, Ezza South L.G.A | EBS/SCPP/LOA/II/298 | 21001001/ 23040101/ 4000005 |  | - | 500000000 | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-06-19 | 2018-07-09 | Completed | 614809322 |  | 96652920 | NIL | NIL | Completed
4 | Works | 7044 | Approval for revised contract sum due to some additional works on the Landscaping of Ezzamgbo, General Hospital Ohaukwu. LGA | EBS/SCPP/LOA/II/299 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-06-19 | 2018-07-09 | Completed |  |  | 226464958.17 | NIL | NIL | Completed
5 | Works | 7044 | Approval for the revised contract sum due to additional works on the landscaping of Owutu-Edda General Hospital , Afikpo South L.G.A | EBS/SCPP/LOA/II/300 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-06-19 | 2018-07-09 | Completed |  |  | 175867356 | NIL | NIL | Completed
6 | Works | 7044 | Approval For The Revised Contract Sum Additional Works On The Landscaping Of Ndufu-Alike Ikwo General Hospital, Ikwo L.G.A | EBS/SCPP/LOA/II/301 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-06-19 | 2018-07-09 | Completed |  |  | 67752762 | NIL | NIL | Completed
7 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping Onicha, General Hospital, Onicha L.G.A | EBS/SCPP/LOA/II/302 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-06-19 | 2018-07-09 | Completed |  |  | 231881546.96 | NIL | NIL | Completed
8 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of Elinwvo General Hospital, Abakaliki | EBS/SCPP/LOA/II/303 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-08-23 | 2018-06-19 | 2018-07-09 | Completed |  |  | 87747420.79 | NIL | NIL | Completed
9 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of General Hospital, Ishiagu, Ivo L.G.A | EBS/SCPP/LOA/II/304 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-09 | Completed |  |  | 137509257.9 | NIL | NIL | Completed
10 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of General Hospital, Ebonyi L.G.A | EBS/SCPP/LOA/II/305 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-10 | Completed |  |  | 75472530 | NIL | NIL | Completed
11 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of Iboko General Hospital, Izzi L.G.A | EBS/SCPP/LOA/II/306 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-10 | Completed |  |  | 127674847.78 | NIL | NIL | Completed
12 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of Itim-Ukwu General Hospital, Afikpo L.G.A | EBS/SCPP/LOA/II/307 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-10 | Completed |  |  | 92701770 | NIL | NIL | Completed
13 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of General Hospital, Okposi, Ohaozara L.G.A | EBS/SCPP/LOA/II/308 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-10 | Completed |  |  | 74882640 | NIL | NIL | Completed
14 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of General Hospital, Agba, Ishielu L.G.A | EBS/SCPP/LOA/II/309 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-10 | Completed |  |  | 83530650 | NIL | NIL | Completed
15 | Works | 7044 | Approval for the revised Contract sum due to some additional works on the landscaping of General Hospital, Umuezeoka, Ezza North L.G.A | EBS/SCPP/LOA/310 | 21001001/ 23040101/ 4000005 |  | - |  | 2018 Budgetary provision | Yes | Open Competitive Tendering | 2018-04-04 | 2018-06-19 | 2018-07-10 | Completed |  |  | 95776432.5 | NIL | NIL | Completed