## Sheet1
PROCUREMENT PLAN
MINISTRY OF POWER AND ENERGY, 2018 FISCAL YEAR.
S/N | CLASS | UNSPC(PROJECT CLASSIFICATION) |  |  | DESCRIPTION | [6 empty] | REF NO |  |  |  | PROJECT CODE |  |  | UNIT OF MEASURE
| A | B |  |  | C | [6 empty] | D |  |  |  | E |  |  | F
1 | Goods | 39120000 |  |  | Installation of 80 Nos solar power street lights and rehabilitation of the existing Electricity Network at the NYSC orientation camp mangregor Afikpo North L.G.A | [6 empty] | EBS/SCPP/LOA/III/346 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 80Nos
2 | Supply | 39120000 |  |  | Contract for distinction for the Extension of Electricity from Igbankpa play ground to Ngamgbo Okeitumo junction in Ettan Community in Ikwo South Constituency Ikwo L.G.A | [6 empty] | EBS/SCPP/LOA/III/265 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | -
3 | Supply | 39120000 |  |  | Contract for the Rural Electrification of Oferkpe Agbaja Community in Izzi L.G.A | [6 empty] | EBS/SCPP/LOA/III/260 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | -
4 | Supply | 39120000 |  |  | Contract for the installation of solar street light at 3 Nos Police Division Areas Command and 21 Police Division in Ebonyi State. | [6 empty] | EBS/SCPP/LOA/III/294 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 3Nos
5 | Supply | 39120000 |  |  | Contract for the Electricity extension on mirror HV rehabilitation and installation of 2 No 300KVA 33/0415K transformer at Afikpo North East Constituency Afikpo North L.G.A | [6 empty] | EBS/SCPP/LOA/III/312 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 3KVA33/ 0415K
6 | Supply | 39120000 |  |  | Contract for the procurement and installation on Thirty Five (35) solar power street light at Afikpo South East Constituency in Afikpo South L.G.A | [6 empty] | EBS/SCPP/LOA/III/264 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 35 Nos
7 | Supply | 39120000 |  |  | Award of contract for the installation of 54 Nos hybrid solar powered street light in the High court Premises Abakaliki. | [6 empty] | EBS/SCPP/LOA/III/369 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 54 Nos
8 | Supply | 39120000 |  |  | Award of contract for the installation of 92 Nos hybrid solar powered street light at Cas Campus in Ebonyi State University, Abakaliki Ebonyi State. | [6 empty] | EBS/SCPP/LOA/III/367 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 92Nos
9 | Supply | 39120000 |  |  | Award of contract for the transmission of 270KVA solar power plant from EBSU TO Energize 150 Nos watts led street lights fittings from EBSU Permanent site entrance gate to the university environs. | [6 empty] | EBS/SCPP/LOA/III/368 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 270 Kva 150 Nos
10 | supply | 39120000 |  |  | Rehabilitation of vandalized 33KVA line and transformer substation at Ihie, federal College of Agriculture and Mile Areas of Ishiagu in Ivo L.G.A | [6 empty] | EBS/SCPP/LOA/II/268 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | 33KVA
11 | supply | 39120000 |  |  | Installation of hybrid solar powered street by St. Patrick’s Kpirikpiri Abakaliki Ebonyi State. | [6 empty] | EBS/SCPP/LOA/II/345 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | -
12 | supply | 39120000 |  |  | Award of contract for a Electricity extension maintenance and Energization of 1 No 500KVA, 33/0.415 Transformer at Ndioke and Nguzu wards in Afikpo South L.G.A. | [6 empty] | EBS/SCPP/LOA/III/257 |  |  |  | 61003001/ 23020103/ 14000010 |  |  | -
13 | supply | 103 |  |  | Approval for the construction of 1 No generator house at the school of Nursing and Mid-wifery Presbyterian join hospital Uburu. | [6 empty] | EBS/SCPP/LOA/II/356 |  |  |  | 61003001/ 23020103/ 14000045 |  |  | -
14 | supply | 103 |  |  | Construction of perimeter fencing and landscaping of the generator and solar power house, opposite international market, Abakaiki | [6 empty] | EBS/SCPP/LOA/II/365 |  |  |  | 61003001/ 23020103/ 14000001 |  |  | -
15 | Works | 103 |  |  | Construction of eight (8) unit of solar power house for the installation of 100KVA, solar component at Uburu school of Nursing and Mid-Wifery, Federal Road by Governor’s House Ezzamgbo school of Health Technology, Afor Enuegu Onicha, Ministry of power and Energy, EBBC, Ministry of Health and Ikwo College of Education. | [6 empty] | EBS/SCPP/LOA/II/345 |  |  |  | 61003001/2 3020103/14 00038 |  |  | 100KVA
PROCUREMENT PLAN
MINISTRY OF POWER AND ENERGY, 2018 FISCAL YEAR.
S/N | ENVISAGED QUANTITY |  | ESTIMATED BUDGET |  |  | SOURCES OF FUND |  | PREQUALIFICAT ION (Y/N) | PROCUREMEN T METHOD |  | ADVERT PUBLICATIO N |  |  | ESTIMATED DATES |  |  |  | PROJECT COMPLETION
[14 empty] | AWARD | PROJECT START
| G |  | H |  |  | I |  | J | K |  | L |  |  | M | N |  |  | O
1 | 80 Nos |  | 350000000 |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-08-10 |  |  | 2018-10-08 | 2018-11-06 |  |  | 12Months
2 | - |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-02-02 |  |  | 2018-04-30 | 2018-05-29 |  |  | Completed
3 | - |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-02-02 |  |  | 2018-04-30 | 2018-05-29 |  |  | Completed
4 | 3 Nos |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-03-23 |  |  | 2018-05-22 | 2018-06-20 |  |  | Completed
5 | 3KVA 33/0415K |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-04-25 |  |  | 2018-06-22 | 2018-07-23 |  |  | Completed
6 | 35 Nos |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-02-02 |  |  | 2018-04-30 | 2018-05-29 |  |  | Completed
7 | 54 Nos |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-10-05 |  |  | 2018-11-29 | 2018-12-29 |  |  | Completed
8 | 92 Nos |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-10-02 |  |  | 2018-11-29 | 2018-12-28 |  |  | Completed
9 | 150 Nos |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-10-02 |  |  | 2018-11-29 | 2018-12-28 |  |  | Completed
10 | 270 Kwh 150 Nos 33 KVA |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-02-02 |  |  | 2018-04-30 | 2018-05-29 |  |  | Completed
11 | - |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-07-27 |  |  | 2018-09-25 | 2018-10-24 |  |  | Completed
12 | - |  |  |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-02-02 |  |  | 2018-04-30 | 2018-05-29 |  |  | Completed
13 | - |  | 5313275.04 |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-08-28 |  |  | 2018-10-25 | 2018-11-23 |  |  | Completed
14 | - |  | 500000000 |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-09-27 |  |  | 2018-11-26 | 2018-12-25
15 | - |  | 62494432.5 |  |  | Budgetary Provision |  | Yes | Open Competitive Tendering |  | 2018-07-27 |  |  | 2018-09-25 | 2018-10-24
PROCUREMENT PLAN
MINISTRY OF POWER AND ENERGY, 2018 FISCAL YEAR.
S/N | REVISED BUDGET AMOUNT |  |  | ACTUAL EXPENDITURE AT: (PROVIDED DATES) |  |  | ACTUAL EXPENDITURE AMOUNT |  |  | BALANCE AT: (PROVIDED DATES) |  |  | BALANCE AMOUNT |  |  |  | COMMENT
| P |  |  | Q |  |  | R |  |  | S |  |  | T |  |  |  | U
1 | 350000000 |  |  | 2018 |  |  | 45217501.28 |  |  | NIL |  |  | NIL |  |  |  | Completed
2 |  |  |  | 2018 |  |  | 22400000 |  |  | NIL |  |  | NIL |  |  |  | Completed
3 |  |  |  | 2018 |  |  | 21552985.68 |  |  | NIL |  |  | NIL |  |  |  | Completed
4 |  |  |  | 2018 |  |  | 60000000 |  |  | NIL |  |  | NIL |  |  |  | Completed
5 |  |  |  | 2018 |  |  | 22400000 |  |  | NIL |  |  | NIL |  |  |  | -
6 |  |  |  | 2018 |  |  | 22400000 |  |  | NIL |  |  | NIL |  |  |  | Completed
7 |  |  |  | 2018 |  |  | 27000002.97 |  |  | NIL |  |  | NIL |  |  |  | Completed
8 |  |  |  | 2018 |  |  | 46300102.04 |  |  | NIL |  |  | NIL |  |  |  | Completed
9 |  |  |  | 2018 |  |  | 68700897 |  |  | NIL |  |  | NIL |  |  |  | Completed
10 |  |  |  | 2018 |  |  | 22400000 |  |  | NIL |  |  | NIL |  |  |  | Completed
11 |  |  |  | 2018 |  |  | 66600000 |  |  | NIL |  |  | NIL |  |  |  | Completed
12 |  |  |  | 2018 |  |  | 22400000 |  |  | NIL |  |  | NIL |  |  |  | Completed
13 | 5313275.04 |  |  | 2018 |  |  | 24906595.69 |  |  | NIL |  |  | NIL |  |  |  | Completed
14 | 500000000 |  |  | 2018 |  |  | 29945469.27 |  |  | NIL |  |  | NIL |  |  |  | Completed
15 | 62494432.5 |  |  | 2018 |  |  | 208314775 |  |  | NIL |  |  | NIL |  |  |  | Completed