## Sheet1
MINISTRY OF WORK AND TRANSPORT, 2019 FISCAL YEAR
PROCUREMENT PLAN FOR THE YEAR 2019
| Procuring Entry Name | Ministry of Work And Transport, 2018 Fiscal Year
2 | Procurement Plan for the Year | 2019
3 | Version
4 | Date Last Updated
5 | Comment
6
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenses At:(Provided Dates) | Actual Expenditure Amount | Balance At: (Provided Dates) | Balance Amount | Comment
1 | Works | 72141000 | Approval for the revised contract for the construction of Uburu Akaeze, road (13.9km) with additional three (3) spam reinforced concrete bridge across Ivo River. | EBS/SCPP/LOA/IV/416 | 34001001/ 23020118/ 17000059 | 13.9km | 13.9km | 1000000000 | Budgetary Provision | Yes | Open Contracting | 2019-03-22 | 2019-05-30 | 2019-06-26 | 12Months | 1000000000 | 2019 | 2473243933.26 | NIL | NIL | Completed
2 | Works | 72141000 | Approval for the revised contract sum due to some additional works on the construction of 2 Nos 2 span bridges to 5.5M triple cell box culvert and 1 No 2 span bridge along Ishieke Odomoke road. | EBS/SCPP/LOA/IV/417 | 34001001/ 23020118/ 17000073 | 2 (5.5MX5.5M) | 2 (5.5mx5.5m) | 1000000000 | Budgetary Provision | Yes | Open Contracting | 2019-03-18 | 2019-05-30 | 2019-06-26 | 12Months | 150000000 | 2019 | 339092074.7 | NIL | NIL | Completed
3 | Works | 72141000 | Approval for the revised contract for the construction of Okoffia internal road (5km) to accommodate 10km (Drainage) | EBS/SCPP/LOA/IV/418 | 34001001/ 23020118/ 17000058 | 5KM | 5km | 300000000 | Budgetary Provision | Yes | Open Contracting | 2019-03-19 | 30/05/20219 | 2019-06-17 | 12Months | 0 | 2019 | 690680637.15 | NIL | NIL | Completed
4 | Works | 72141000 | Approval for the revised contract sum of the reconstruction of Amasiri – Owutu – Oso Edda Road to continue from Ebunwana – Ekoli Nguzu Road (5km) | EBS/SCPP/LOA/IV/441 | 34001001/ 23020118/ 17000014 | 5KM | 5km | 500000000 | Budgetary Provision | Yes | Open Contracting | 2019-07-24 | 2019-09-02 | 2019-09-30 | 12Months | 500000000 | 2019 | 422656500 | NIL | NIL | Completed
5 | Works | 72141000 | Reconstruction of Ntezi Road to – Agba Isu Road (15km) | EBS/SCPP/LOA/IV/447 | 34001001/ 23020118/ 17000013 | 5KM | 15km | 1000000000 | Budgetary Provision | Yes | Selective Tendering | 2019-07-24 | 2019-09-13 | 2019-10-18 | 12Months | 1000000000 | 2019 | 2006787517.09 | NIL | NIL | Completed
6 | Works | 72141000 | Construction of Obujia – Nwanwu Road (9.8km) | EBS/SCPP/LOA/IV/446 | 34001001/ 23020118/ 17000039 | 9.8km | 9.8km | 500000 | Budgetary Provision | Yes | Selective Tendering | 2019-07-15 | 2019-09-13 | 2019-09-30 | Completed | 1000000000 | 2019 | 1,244,115,556,09 | NIL | NIL | Completed
7 | Works | 72141000 | Reconstruction of Mpu Road to junction of Obiozara Federal road | EBS/SCPP/LOA/IV/453 | 34001001/ 23022018/ 17000089 |  |  | 1000000000 | Budgetary Provision | Yes | Open Contracting | 2019-08-05 | 2019-10-14 | 2019-11-04 | Completed | - | 2019 | 1669043500 | NIL | NIL | Completed
8 | Works | 72141000 | Construction of Umuchima Enuebu Road in Ohaozara L.G.A (6KM) | EBS/SCPP/LOA/IV/455 | 34001001/ 23022018/ 17000008 | 6km | 6km | 500000000 | Budgetary Provision | Yes | Selective Tendering | 2019-08-10 | 2019-10-24 | 2020-01-05 | Completed | 1000000000 | 2019 | 536558400 | NIL | NIL | Completed