## Sheet1
MINISTRY OF HEALTH, 2019FISCAL YEAR
PROCUREMENT PLAN FOR THE YEAR 2019
1 | Procuring Entry Name | Ministry of Health, 2019 Fiscal Year
2 | Procurement Plan for the Year | 2019
3 | Version
4 | Date Last Updated
5 | Comment
6
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenses At:(Provided Dates) | Actual Expenditure Amount | Balance At: (Provided Dates) | Balance Amount | Comment
1 | Works | 7044 | Award of contract for the construction of Hostel block (Lot 1A) at the Ebonyi State University Teaching Hospital, Uburu, Ohaozara Local Govt. Area | EBS/SCPP/LOA/IV/425 | 21001001/ 23010139/ 400036 | - | - | 1500000000 | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-08-01 | Completed | 294885086 | 2019 | 294885085.75 | NIL | NIL | Completed
2 | Works | 7044 | Award of contract for the construction of Hostel block (Lot 1B) at the EBSU Teaching Hospital, Uburu, Ohaozara L.G.A | EBS/SCPP/LOA/IV/426 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-08-01 | Completed | 294885086 |  | 294885085.75 | NIL | NIL | Completed
3 | Works | 7044 | Award of contract for the construction of Hostel block (Lot 1C) at the EBSU Teaching Hospital, Uburu, Ohaozara L.G.A | EBS/SCPP/LOA/IV/427 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-08-01 | Completed | 2650338344 |  | 294885085.75 | NIL | NIL | Completed
4 | Works | 7044 | Award of contract for the construction of Hospital block (Lot 1D) at the EBSU Teaching Hospital, Uburu,Ohaozara Local Govt. Area | EBS/SCPP/LOA/IV/428 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-08-01 | Completed | 294885086 |  | 294885085.75 | NIL | NIL | Completed
5 | Works | 7044 | Award of contract for the construction of Junior Staff Quarters (Lot 1E) at the EBSU Teaching Hospital, Uburu, Ohaozara L.G.A | EBS/SCPP/LOA/IV/429 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-08-01 | Completed | 250971714 |  | 250971713.75 | NIL | NIL | Completed
6 | Works | 7044 | Award of contract for the construction of Junior Staff (Lot 1F) at the EBSU Teaching Hospital, Uburu, Ohaozara L.G.A | EBS/SCPP/LOA/IV/430 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-07-24 | Completed | 250971714 |  | 250971713.75 | NIL | NIL | Completed
7 | Works | 7044 | Award of contract for the construction of Senior Staff Quarters (Lot 1G) at the EBSU Teaching Hospital, Ohaozara L.G.AUburu, | EBS/SCPP/LOA/IV/431 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-07-24 | Completed | 299381625 |  | 299381625.31 | NIL | NIL | Completed
8 | Works | 7044 | Award of contract for the construction of Hospital block (1H) | EBS/SCPP/LOA/IV/432 | 21001001/ 23010139/ 400036 | - |  |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-07-24 | Completed | 299381625 |  | 299381625.31 | NIL | NIL | Completed
9 | Works | 7044 | Award of contract for the construction of Hospital block (Lot II) at the EBSU Teaching Hospital, Uburu Ohaozara L.G.A | EBS/SCPP/LOA/IV/433 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-19 | 2019-07-11 | 2019-07-24 | Completed | 2941194786 |  | 2941194786.11 | NIL | NIL | Completed
10 | Works | 7044 | Award of contract for the construction of utility Building (Lot II) at EBSU Teaching Hospital Uburu Ohaozara L.G.A | EBS/SCPP/LOA/IV/434 | 221001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2019-05-24 | 2019-07-11 | 2019-07-24 | Completed | 1293228865 |  | 1293228865.18 | NIL | NIL | Completed
11 | Works | 7044 | Award of contract for the construction of school block (Lot IL) at EBSU Teaching Hospital, Uburu, Ohaozara L.G.A | EBS/SCPP/LOA/IV/435 | 21001001/ 23010139/ 400036 | - | - |  | 2019 Budgetary provision | Yes | Open Competitive Tendering | 2018-12-23 | 2019-01-18 | 2019-07-24 | Completed | 2853039084.9 |  | 2650338534.43 | NIL | NIL | Completed