## Sheet1
EBONYI PROCURMENT PLAN TEMPLATE
| A | B | C | D | E | F | G | H | I | J | K | L | M | N
Procuring Entity Name: Ministry of Housing and Urban Development
Procurement plan for the Year: 2023
Date created: 31-01-2023
Comments
Estimated Dates
| Class | UNSPSC | Description | RefNo | Unit | Envis aged Quant ity | Estimated Budget | Source of Funds | Prequ alificat ion (Y/N) | Procurement Method | Ad ver t Pu | Awa rd Date | Projec t Start | Projec t Compl etion | Cost of Projec t
1 | Works | 062530010001 | Completion of Centenary City Secretariat |  |  |  | 50,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Mar-23 | Aug- 23
2 | Works | 062530010002 | Furnishing of offices for Ministry of Housing and |  |  |  | 5,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Mar-23 | Apr-23
3 | Works | 062530010006 | Rehabilitation of New Government House Building, Governor’s (Lodge & office) and Presidential Lodge. |  |  |  | 50,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Apr-23 | Jun-23
4 | Works | 062530010007 | Rehabilitation Presidential Lodge |  |  |  | 20,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Apr-23 | Jun-23
5 | Works | 062530010008 | Rehabilitation of Ecumenical Centre |  |  |  | 20,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | May-23 | Jul-23
6 | Works | 062530010009 | Swimming pool for Governor’s Lodge |  |  |  | 5,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | May-23 | Jun-23
7 | Works | 062530010010 | Tennis Court for Governor’s Lodge |  |  |  | 5,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Apr-23 | May-23
8 | Works | 062530010012 | Rehabilitation of New Exco chambers building |  |  |  | 5,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Jun-23 | Jun-23
9 | Works | 062530010013 | Her Excellency’s New office |  |  |  | 5,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Apr-23 | May-23
10 | Works | 062530010014 | Internal and External fencing of the New |  |  |  | 10,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Mar-23 | May-23
11 | Works | 062530010016 - | Rehabilitation of new Government House Chapel & |  |  |  | 5,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | May-23 | un-23
12 | Works | 062530010021 - | Construction of one Storey Building at new |  |  |  | 20,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Mar-23 | ct-23
13 | Works | 062530010023 - | Construction of one Storey Building at new |  |  |  | 20,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Mar-23 | ov-23
14 | Works | 062530010024 - | Construction of Concrete Line Drain at Abakaliki |  |  |  | 20,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Apr -23 | un-23
15 | Works | 062530010032 - | Rehabilitation of Shopping Mall |  |  |  | 10,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Apr -23 | ug-23
16 | Works | 062530010034 - | Agugwu Church, Uburu |  |  |  | 100,000,000.0 0 | 2023 Budget provision | Yes | eprocurement |  |  | May -23 | un-23
17 | Works | 062530010035 - | Construction of new Buildings, in new Government House Abakaliki___ |  |  |  | 50,000,000.00 | 2023 Budget provision | Yes | eprocurement |  |  | Jun- 23 | ec-23
18 | Works | 062530010033 - | Development of new Housing units for____Civil____and |  |  |  | 1,000,000,000 .00 | 2023 Budget provision | Yes | eprocurement |  |  | Mar-23 | ec-23