## Sheet1
EBONYI STATE PROCUREMENT PLAN TEMPLATE
S/ N | A |  | B | C | D | E | F | G | H | I | J | K | L | M | N | O
1 | PROCURING ENTITY NAME: MINISTRY OF LANDS
2 | PROCUREMENT PLANT FOR YEAR:2023
3 | DATE CREATED:2023
4 | COMMENTS
5
6
7 | Class | UNSPSC Projects Classificatio n |  | Descriptio n | R ef N o | Un it | Envisag ed Quantit y | Estimate d Budget | Source Of Fund | Prequalifica tion Y/N | Procurem ent Method | Advert Publicati on Date | Awar d Date | Proje ct Start Date | Project Complet ion date | Cost of Projectio n
8 | Acquisition of lands for:i.Federal Govt. assisted New National Housing programmed 5 Hectares).ii.St ate Housing programme for the 3 senatorial zones(50 hectares).iii.O ther various Government projects including establishmen t of new layouts(75 hectares) | 062600010 001 |  | Land Developm ent |  |  | 150 hectare s | 85,000,0 00 | 2023 Budge t Provisi on | Nil | Direct Labour | 20/3/23 | 10/4/ 23 | 11/4/ 23 | 09/5/23 | 85,000,0 00
S/ N | Class | UNSPSC Projects Classificatio n | Descriptio n | R ef N o | Un it | Envisag ed Quantit y | Estimate d Budget | Source Of Fund | Prequalifica tion Y/N | Procurem ent Method | Advert Publicati on Date | Awar d Date | Proje ct Start Date | Project Complet ion date | Cost of Projectio n
9 | Payment of compensatio n. i Outstanding ii New Aquisition | 062600010 002 | B: Payment of compensa tion to land owners affected by Govt .Acquisitio n; F: 300,000, 000; G: 2023 Budge t Provisi on; H: Nil; I: Direct Labour; L: 13/3/ 23; M: 13/12/2 3; N: 300,000, 000
10 | System Upgrading of Automation | 062600010 025 | B: System Upgrading; F: 200,000, 000; G: 2023 Budge t Provisi on; H: Nil; I: Direct Labour; L: 01/3/ 23; M: 26/4/23; N: 200,000, 000
11 | Installation of Automation machine | 062600010 003 | B: Installatio n; F: 40,000, 000; G: 2023 Budge t Provisi on; H: Nil; I: Direct Labour; L: 01/3/ 23; M: 26/4/23; N: 40,000, 000
S/N | A | B ¦ C |  | D | E | F | G | H | I | J | K | L | M | N | O
| PROCUREMENT ENTITY’S NAME: OFFICE OF THE SURVEYOR-GENERAL PROCUREMENT PLAN FOR YEAR: 2023 DATE CREATED : 2023 COMMENTS |  |  | M: Estiff; N: iated Date; O: is
| Class | UNSPSC Project Classification | Description | Ref No. | Unit | Envisaged Quantity | Estimated Budget (N) | Source of fund | Prequali fication (Y/N) | Procure ment method | Advert publica tion | Award Date | Project start Date | Project complet ion Date | Cost of project
1 | Goods | 062600020001 | Procurement of digital survey equipment |  |  | 1 | 6,000,000.00 | State Govt. fund | No | Direct Labour | Nil | Nil | Jan. 2023 | Dec. 2023 | 6,000,000.00
2 | Works | 062600020002 | Digitalization and upgrading of Analogue Maps/plans in Abakaliki |  |  |  | 6,000,000.00 | State Govt. fund | No | Direct Labour | Nil | Nil | Jan. 2023 | Dec. 2023 | 6,000,000.00
3 | Works | 062600020003 | Densification/establis hment of control in Abakaliki urban |  |  |  | 4,000,000.00 | State Govt. fund | No | Direct Labour | Nil | Nil | Jan. 2023 | Dec. 2023 | 4,000,000.00
4 | Works | 062600020007 | Digitalization of all Government Layout with Geographical Information System (GIS) |  |  |  | 4,000,000.00 | State Govt. fund | No | Direct Labour | Nil | Nil | Jan. 2023 | Dec. 2023 | 4,000,000.00
5 | Works | 062600020004 | Perimeter/Parcelation /Survey of newly acquired areas in Abakaliki |  |  |  | 2,000,000.00 | State Govt. fund | No | Direct Labour | Nil | Nil | Jan. 2023 | Dec. 2023 | 2,000,000.00