## Sheet1
MINISTRY OF HEALTH
| A | B | C | D | E F G H |  |  |  | I | J | K | L | M | N | O
Procuring Entity Name: Ministry of Health
Procurement Plan for year: 2024
Date Created: 08/01/2024
Comments:
|  |  | Description | [9 empty] | Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  | COST | Ref No | Unit | Envisaged Quantity | Estimated Budget | Source of Funds | Prequal ificatio n (Y/N) | Procurem ent Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
1 | Works | 0405012400201 | Renovation of 8 Nos General Hospitals | 100,000,000.00 |  |  | 8 | 100,000,000.00 | 2024 Budgetary Provision |  | e- procure ment |  |  | Feb 2024 | Dec.2024
2 | Goods | 0406012400501 | Provision of essential drugs to General Hospitals/ PHC (Drug revolving fund) | 50,000,000.00 |  |  | 14 | 50,000,000.00 | 2024 Budgetary Provision |  | e- procure ment |  |  | March 2024 | Dec.2024
3 | Goods | 0406012400060 2 | Procurement of essential commodities for malarial elimination programme (LLINs, MRDT, ACTs & SP) | 50,000,000.00 |  |  |  | 50,000,000.00 | 2024 Budgetary Provision |  | e- procure ment |  |  | Feb 2024 | Dec.2024
4 | Goods | 0406012400701 | Procurement of essential consumables for NIGEP Surveillance and Other emergency response to Epidemic Diseases Control | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
5 | Servic es | 0406022400010 2 | Neglected Tropical Diseases (NTDs) | 5,000,000.00 |  |  |  | 5,000,000.00 | 2024 Budgetary Provision |  | e- procurem ent |  |  | Feb.2024 | Dec.2024
6 | Goods | 0405032400020 2 | Procurement of essential commodities for Free Maternal and New Born | 20,000,000.00 |  |  |  | 20,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan.2024 | Dec.2024
7 | Goods | 0405022240001 03 | Procurement of HIV Rapid Test Kits, PMTC commodities and other consumables for HIV/AIDS/ Hepatitis Interventions across the State. (SOML P for R) | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | March 2024 | Dec.2024
8 | Goods | 0405012400050 3 | Provision of medical equipment for School Health Services | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | March 2024 | Aug.2024
9 | Goods | 0401012400010 3 | Procurements of books for Health Education Services | 5,000,000.00 |  |  |  | 5,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | Aug.2024
10 | Works | 0405012400070 3 | Revitalization and maintenance of 3nos Incinerator system in 3 GHs at the 3 senatorial zones for disposal of medical waste in the state | 20,000,000.00 |  |  | 3 | 20,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
11 | Works | 0405012400080 3 | Construction/Maintenan ce of 1No. Parma Grade Central Medical Store at the Centenary City for | 50,000,000.00 |  |  | 1 | 50,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
Drug Distribution.
12 | Servic es | 0407032400010 1 | Maternal New born and Child Health Week | 30,000,000.00 |  |  |  | 30,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
13 | Works | 0405032400030 3 | Provision & reticulation of water in 26 (2 per LGA) out of the 171 PHCs | 80,000,000.00 |  |  | 26 | 80,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
14 | goods | 0405032400040 1 | Provision of alternative power source in some LGAs out of the 171 PHC | 50,000,000.00 |  |  |  | 50,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June.2024
15 | Works | 0405012401001 | Construction of 3 major cold store in each senatorial zone of the state, to serve in distributions of both routine and non-routine drugs | 40,000,000.00 |  |  | 9 | 40,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
16 | Goods | 0406012400080 1 | Procurement of Mama Kits and essential drugs and BEMONC for Reproductive Health services across the State (SOML P for R) | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | July.2024
17 | Goods | 0405032400050 1 | Procurement of PPLARC, MVA equipment and consumables for Family Planning Services at General Hospitals/PHC | 10,000,000.00 |  |  | 8 | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June.2024
18 | Goods | 0405012400110 | Procurement of 1No of Cold Van for delivery of | 50,000,000.00 |  | 50m | 1 | 50,000,000.00 | 2024 Budgetary |  | e-procurem |  |  | March 2024 | July.2024
|  | 3 | drugs/Logistics Management Coordinating Unit (LMCU) operational activities | [5 empty] | Provision |  | ent
19 | Goods | 0401022400010 3 | Production of ANNUAL HUMAN RESOURCE FOR Health FROM THE STATE HEALTH workforce registry for Medical Records | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
20 | Goods | 0407032400040 1 | Production of State Health Account for optimization of health financing | 5,000,000.00 |  |  | 1 | 5,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June.2024
21 | Goods | 0410012400204 | Procurement of Office Furniture (Permanent Secretary's office) | 2,000,000.00 |  |  |  | 2,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
22 | Works | 0408012400020 4 | Maternal and Perinatal Death Surveillance and Response (MPDSR) Activities | 2,000,000.00 |  |  |  | 2,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
23 | Servic es | 0408022400010 4 | Nigeria filed Epidemiology laboratory (NFELT) Programme | 1,000,000.00 |  |  |  | 1,000,000.00
24 | Works | 0405012400190 3 | Maintenance of 19 nos COVID19 isolation/treatment center and other public health isolation facilities | 1,000,000.00 |  |  | 19 | 1,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | May.2024
25 | Goods | 0407012400010 3 | Procurement of office ICT equipment for operational research | 5,000,000.00 |  |  |  | 5,000,000.00 | 2024 Budge | tary Prov | isione-procurem | Y | es | Jan 2e-0p2ro4cu | reApnlt 2024
ent
26 | Goods | 0450124002603 | Procurement of 2 No. (4 Module) Gene xpert machine for diagnosis of Tuberculosis in the state | 10,000,000.00 |  |  | 2 | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | April.2024
27 | Works | 0405012400270 3 | Maintenance/Equipping of standard Medical Laboratory in the 14 general hospitals | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision | Yes | e-procurem ent |  |  | Jan 2024 | Dec.2024
28 | Goods | 0405012400280 1 | Procurement of oxygen cylinders/heads in the 171 PHCs and 171 nebulizers. | 15,000,000.00 |  |  | 171 | 15,000,000.00 | 2024 Budgetary Provision | Yes | e-procurem ent |  |  | Jan 2024 | Dec.2024
29 | Works | 0405012400290 1 | Renovating/Equipping of drug stores in the 13 LGA across the state | 10,000,000.00 |  |  | 13 | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
30 | Goods | 0407012400010 3 | Printing of Health Management Information System Data Reporting Tools for the state | 10,000,000.00 |  |  |  | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | May.2024
31 | Goods | 0405012400300 1 | Procurement of equipment/machines for Pharmacovigilance in the State (DPS, 14 general hospitals and LGAs) | 10,000,000.00 |  |  | 14 | 10,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | April 2024 | July.2024
32 | Works | 0402012400030 | CCD Intervention in 1 community each in the 3 | 150,000,000.00 |  |  | 3 | 150,000,000.00 | 2024 Budgetary |  | e-procurem |  |  | Jan 2024 | Dec.2024
|  | 3 | senatorial Zones | [5 empty] | Provision |  | ent
33 | works | 0405224000303 | Implementation of IMPACT programme in the State | 239,000,000.00 |  |  |  | 239,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Aug.2024
34 | Goods | 0406012400100 3 | Procurement of medical consumables for Nutrition Department to combat acute malnutrition in the State | 150,000,000.00 |  |  |  | 150,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | March 2024 | Sept.2024
35 | Works | 0405012400303 | Construction and Furnishing of 6 No. 2 Bedroom flats for health workers accommodation in the 14 General Hospitals | 3,000,000,000. 00 |  |  | 6 | 3,000,000,000. 00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
36 | Works | 0405012400330 3 | Construction of 3Nos. Newborn Centers in the State | 50,000,000.00 |  |  | 3 | 50,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
37 | Servic es | 0401022400020 3 | Implementation of Ebonyi State Council on Health programme | 20,000,000.00 |  |  |  | 20,000,000.00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb.2024 | Dec.2024
38 | Works | 0405012400350 3 | Construction of 4 No. New General Hospitals. | 1,000,000,000. 00 |  |  | 4 | 1,000,000,000. 00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
| Works | 0405012400360 3 | Construction of Ebonyi State Diagnostic Center | 3,000,000,000. 00 |  |  |  | 3,000,000,000. 00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
| Servic es | 0402012400040 3 | Free Mobile Clinic/ Health Awareness Campaign | 700,000,000,00 |  |  |  | 700,000,000,00 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Nov. 2024