## Sheet1
MINISTRY OF AGRICULTURE AND NATURAL RESOURCES
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
Procuring Entity Name: Ministry of Agriculture and Natural Resources
Procurement Plan for year: 2024
Date Created: 17/01/2024
Comments:
Estimated Dates
S/N | Class | UNSPSC (Project Classification) | Description | COST | Ref No | Unit | Envisaged Quantity | Estimated Budget | Source of Funds | Prequal ification (Y/N) | Procurem ent Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
1 | Works | 23020101 | Construction of Perimeter fence of Market Garden Ohatekwe Ebonyi LGA | 30000000 |  | s |  | 30000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
2 | Goods | 23020101 | Empowerment of Ebonyi State farmers by providing access to credit facilities. | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | March 2024 | Aug, 2024
3 | Goods | 23010107 | Purchase of newHp tractors with implements plough, harrowplanters, boom sprayer and 7.5-15Hp power tiller /smart tractor, irrigation equipment and post harvest equipment | 360000000 |  |  |  | 360000000 | 2025 Budgetary Provision |  | e- procure ment |  |  | Feb. 2024 | Aug.2024
4 | Works | 23030112 | Rehabilitation of zonal veternary clinic at onueke and afikpo north | 50000000 |  |  |  | 50000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
5 | Goods | 23010113 | Purchase of 2Nos set of Computers for Hon. Comm , Perm sec and 3no laptops for PRS,Account dept and Admin | 3000000 |  |  |  | 3000000 | 2024 Budgetary Provision |  | e- procurem ent |  |  | Jan, 2024 | July, 2024
6 | Goods | 23010115 | Purchase of 2Nos Photocopying machines for commissioner and perm sec offices | 1000000 |  |  |  | 1000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb, 2024 | Aug,.2024
7 | Goods | 23010127 | Providing of agro inputs 13000 rural farmers | 100000000 |  |  | 13000 | 100000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | March, 2024 | June, 2024
8 | Goods | 3010127 | Purchase of Veterinary Pharmaceuticals and vaccines | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb, 2024 | May, 2024
9 | Goods | 23010127 | Purchase of Vet. Clinical and surgical equipment | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb, 2024 | May, 2024
10 | Works | 23020113 - | Construction of state fish farm at the two senatorial zones (central & south) | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec, 2024
11 | Works | 23020113 | Rehabilitation of the pig multiplication units at Ezzamgbo and Afikpo | 12500000 |  |  |  | 12500000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
12 | Works | 23020113 | Rehabilitation of veterinary school and veterinary investigation Centre at Ezzangbo | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June
13 | Works | 23020113 | Establishment of Dairy farm | 50000000 |  |  |  | 50000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | Dec.2024
14 | Works | 23020113 | Establishment of 3 market gardens in the 3 senatorial zones vis: Afikpo North, Ezza South and Ohaukwu | 60000000 |  |  |  | 60000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | Dec.2024
15 | Services | 23050101 | Printing Statutory vet documents certificate | 1000000 |  |  |  | 1000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec, 2024
16 | Works | 23020113 | Construction of Irrigation facilities at Ndieruphu Dam Site Iboko (50 hecteras | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec, 2024
17 | Works | 23030112 | Rehabilitation Item Amagu Irrigation Site (2,500 hectares | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
MINISTRY OF AGRICULTURE AND NATURAL RESOURCES
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
Procuring Entity Name: Ministry of Agriculture and Natural Resources
Procurement Plan for year: 2024
Date Created: 17/01/2024
Comments:
Estimated Dates
S/N | Class | UNSPSC (Project Classification) | Description | COST | Ref No | Unit | Envisaged Quantity | Estimated Budget | Source of Funds | Prequal ification (Y/N) | Procurem ent Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
18 | Works | 23030112 | Rehabilitation of Ezillo Farm Irrigation Scheme (500 hectares) | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
19 | Works | 23020113 | Construction of Irrigation facilities at Ivo Dam site (2000 hectares) and other locations | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
20 | Services | 23050101 | School Agric programme for 3 pilot school | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
21 | Services | 23050101 | Soil Nutrient survey/ analysis | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
22 | Works | 23030112 | Rehabilitation of Rice Mills across the state | 50000000 |  |  |  | 50000000 | 2024 Budgetary Provision |  | e- procurem ent |  |  | Jan 2024 | Dec.2024
23 | Goods/Services | 23050101 - | IFAD VCDP counterpart fund other partnership contributions | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Jun.2024
24 | Works | 23020113 | Agricultural Infrastural development projects in the state (IFAD) | 1500000000 |  |  |  | 1500000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
25 | Goods | 23010127 | Procurement of Cassava Starch & Flour Plants. | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
26 | Goods | 23010127 | Procurement and distribution of Agro-inputs such as fertilizer, improved rice seeds, maize. | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | March, 2024 | Julye.2024
27 | Goods | 23050101 | Agricultural empowerment for women and youths | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June.2024
28 | Goods/Services | 23050101 | Climate Resilient Sustainability Agriculture CRSA/Agric econlogy | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | April.2024
29 | Goods/Services | 23050101 | Agricultural Mechanization (Appropriate Labour Saving Technology) | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | April.2024
30 | Works | 23030112 | Rehabilitation of Nkalilki Hatchery | 300000000 |  |  |  | 300000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
31 | Goods | 23050101 | L- PRES Livestock Productivity and Resilience support programme Counterpart funding. | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | May.2024
32 | Goods | 23010127 | Procurement of miracle oil palm seedlings from Malaysia | 50000000 |  |  |  | 50000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | April.2024
33 | Goods | 23010119 | Purchase of 1no generating set for office use | 500000 |  |  |  | 500000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | July, 2024
34 | Goods | 23010112 | Procurement of office furniture and equipment for Department of PRS, Livestock and Fishery,Food and Nutrition | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
MINISTRY OF AGRICULTURE AND NATURAL RESOURCES
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
Procuring Entity Name: Ministry of Agriculture and Natural Resources
Procurement Plan for year: 2024
Date Created: 17/01/2024
Comments:
Estimated Dates
S/N | Class | UNSPSC (Project Classification) | Description | COST | Ref No | Unit | Envisaged Quantity | Estimated Budget | Source of Funds | Prequal ificatio n (Y/N) | Procurem ent Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
| Works | 23050101 | Irrigation development for Rice farming and crops development | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
35 | Services | 23050101 | Research and Development of improved rice seedlings | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
36 | Services | 23010127 | Purchase of land development Equipment | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | Jan 2024 | Dec.2024
37 | Works | 23030112 | Rehabilitation, Modernization and upgrading of palm oil mill at Owutu Edda | 100000000 |  |  |  | 100000000 | 2024 Budgetary Provision |  | e- procure ment |  |  | March 2024 | Sept.2024
38 | Goods | 23010127 | Purchase of Agricultural mobile pest control equipmen | 9000000 |  |  |  | 9000000 | 2024 Budgetary Provision |  | e- procurem ent |  |  | March 2024 | Oct,.2024
39 | Works | 23020113 | Construction of Veterinary hospital and Standard diagnostic at Abakaliki Headquarte | 60000000 |  |  |  | 60000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | April 2024 | Oct.2024
40 | Works | 23020113 | Construction of 1No office building and 1No warehouse at Ezillo farm | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
41 | Works | 23020113 | Construction of demonstration farms for mobilizing farmers to adopt plant nutritional biofortified crops in the 3 senatorial zones | 30000000 |  |  |  | 30000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June.2024
42 | Goods | 23010139 | Purchase of public address system for enlightenment on need of balance diet for women and children in the 3 senatorial zones - Purchase of Still camera and Camcorder etc | 5000000 |  |  |  | 5000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June.2024
43 | Works | 23020113 | Construction of Shed for protection of equipment | 10000000 |  |  |  | 10000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | April.2024
44 | Works | 23020113 | Construction of cassava processing plant at Ugwulangwu | 30000000 |  |  |  | 30000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | June, 2024
45 | Works | 23020113 | Construction of Pig Multiplication Unit in the 12 L.G.A | 300000000 |  |  | 12 | 300000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Feb 2024 | Dec,.2024
46 | Works | 23020113 | Project on Community Charter of Demand (CCD) | 180000000 |  |  |  | 180000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec, 2024
47 | Goods | 23050101 | Capacity building for fish farmers on extration of fish oil for export | 20000000 |  |  |  | 20000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan, 2024 | June, 2024
48 | Works | 23020113 | Construction of Silos across 13 LGA | 500000000 |  |  | 13 | 500000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | March.2024
49 | Works | 23020113 | Establishemnt of Standard Fish Feed Factory | 150000000 |  |  |  | 150000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024
50 | Works | 23020113 | Establishment of Standard Poultry Feed Factory | 150000000 |  |  |  | 150000000 | 2024 Budgetary Provision |  | e-procurem ent |  |  | Jan 2024 | Dec.2024