## 2020 procurement plan
MINISTRY OF INFRASTRUCTURAL DEVELOPMENT FOR CONCESSION, EBONYI STATE
PROCUREMENT PLAN FOR THE YEAR 2020
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
1 | A: Procuring Entry Name; B: Ministry of Infrastructural Development for Concession
2 | A: Procurement Plan for the year; B: 2020
3 | A: Version; B: 1
4 | A: Date Last Updated; B: 24/11/2020
5 | A: Comment
6
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenditure At:(Provide Dates) | Actual Expenditure Amount | Balance At:(Provide Dates) | Balance Amount | Comment
1 | Works | 103 | Dualization of Abakaliki Enugu Road from EBSU Gate to Ezzamgbo |  |  | km | 3.6km | 200000000 | State Government Fund | No | D/L | - |  | 2019 | 2020 | 400000000 | JAN - OCT | 614003016 | 31/10/2020 | -214003016
2 | Works | 103 | Construction of flyover bridge and retaining wall at Ezzamgbo junction and Ancillary work |  |  | km | 6km | 600000000 | State Government Fund | Yes | D/L | - |  | 2019 | 2020 | 1400000000 | JAN - OCT | 1078163958.5 | 31/10/2020 | 321836041.5
3 | Works | 103 | Dualization of Abakaliki Enugu Road from Ezzamgbo JUNCTION TO Ntezi |  |  | km | 6km | 500000000 | State Government Fund | Yes | D/L | - |  | 2019 | 2020 | 100000000 | JAN - OCT | 0 | 31/10/2020 | 100000000
4 | Works | 103 | Construction of flyover bridge and retaining wall at Nkalagu junction |  |  | km |  | 700000000 | State Government Fund | Yes | D/L | - |  | 2020 |  | 800000000 | JAN - OCT | 750648233.75 | 31/10/2020 | 49351766.25
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenditure At:(Provide Dates) | Actual Expenditure Amount | Balance At:(Provide Dates) | Balance Amount | Comment
5 | Works | 103 | Construction of flyover bridge at water works junction Abakaliki |  |  | km |  | 500000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 100000000 | JAN - OCT | 0 | 31/10/2020 | 100000000
6 | Works | 103 | Dualization of a section of Abakaliki/Afikpo Road from Mammy Market to FUNAI Junction |  |  | km | 4.6km | 350000000 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 700000000 | JAN - OCT | 834200500 | 31/10/2020 | -134200500
7 | Works | 103 | Dualization of a section of Abakaliki-Afikpo road from FUNAI Junction to Amuzu (Drainage Construction) |  |  | km | 8km | 800000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 50000000 | JAN - OCT | 115261200 | 31/10/2020 | -65261200
8 | Works | 103 | Construction of Ezzamgbo Flyover Ancillary works |  |  | km |  | 200000000 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 100000000 | JAN - OCT | 0 | 31/10/2020 | 100000000
9 | Works | 100988 | Value of Work done by Ministry of Infrastructural Development for Concession at Ecumenical centre and shoping mall (Landscaping and concrete pavement) |  |  | km |  | 0 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 0 | JAN - OCT | 0 | 31/10/2020 | 0
10 | Works | 103 | Construction of Nkalagu Flyover Ancillary works |  |  | km |  | 100000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 100000000 | JAN - OCT | 0 | 31/10/2020 | 100000000
11 | Works | 103 | Construction of flyover Bridge at Airport Junction, Onueke, Ezza South LGA. |  |  | km |  | 700000000 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 100000000 | JAN - OCT | 97610000 | 31/10/2020 | 2390000
12 | Works | 103 | Construction of Agba Eguhuo 6 span bridge |  |  | km |  | 0 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 0 | JAN - OCT | 0 | 31/10/2020 | 0
13 | Works | 103 | Dualization of a section of Abakaliki-Enugu road from Ntezi to Ezzillo |  |  | km |  | 300000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 50000000 | JAN - OCT | 0 | 31/10/2020 | 50000000
14 | Works | 103 | Dualization of Abakaliki-Afikpo road from Amuzu to Onueke |  |  | km | 5km | 200000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 50000000 | JAN - OCT | 0 | 31/10/2020 | 50000000
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenditure At:(Provide Dates) | Actual Expenditure Amount | Balance At:(Provide Dates) | Balance Amount | Comment
15 | Works | 103 | Constuction of two span 15m RC bridges at Ezzamgbo |  |  | km |  | 100000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 130000000 | JAN - OCT | 108336825 | 31/10/2020 | 21663175
16 | Works | 103 | Construction of line drainages, culverts within the state |  |  | km |  | 500000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 150000000 | JAN - OCT | 110000000 | 31/10/2020 | 40000000
17 | Goods | 103 | Purchase of construction equipment for Ebonyi state Government work |  |  | km |  | 200000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 80000000 | JAN - OCT | 54329535.53 | 31/10/2020 | 25670464.47
18 | Works | 103 | Construction of Ancillary works, bypass and pedestrian brisges in different locations of the state |  |  | km |  | 200000000 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 50000000 | JAN - OCT | 0 | 31/10/2020 | 50000000
19 | Works | 103 | Construction of bridges within the state and at the new Govenment House |  |  | km |  | 500000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 100000000 | JAN - OCT | 356509980 | 31/10/2020 | -256509980
20 | Goods | 25101507 | Purchase of 2No Hilux Toyota Van |  |  | km |  | 50000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 20000000 | JAN - OCT | 0 | 31/10/2020 | 20000000
21 | Works | 103 | Provision for very urgent works within the state (Installation of H2550 Batching plant) |  |  | km |  | 0 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 10000000 | JAN - OCT | 0 | 31/10/2020 | 10000000
22 | Consulting Services | 81101514 | Geotechnical investigation at Uburu school of Medicine flyover bridge project |  |  | km |  | 0 | State Government Fund | No | D/L | - | 2019 | 2019 | 2020 | 20000000 | JAN - OCT | 0 | 31/10/2020 | 20000000
23 | Works | 103 | Construction of Flyover Bridge at Vanco junction Abakaliki |  |  | km |  | 500000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 100000000 | JAN - OCT | 100000000 | 31/10/2020 | 0
24 | Works | 103 | Construction of flyover bridge at Amasiri Junction |  |  | km |  | 500000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 50000000 | JAN - OCT | 0 | 31/10/2020 | 50000000
25 | Works | 103 | Construction of flyover bridge at Uburu Onuafukwu Junction |  |  | km |  | 500000000 | State Government Fund | No | D/L | - | 2020 | 2020 | 2020 | 800000000 | JAN - OCT | 968412518.3 | 31/10/2020 | -168412518.3