## Table 1
MINISTRY OF WORK AND TRANSPORT
| A | B | C |  | D | E |  | F |  |  | G |  | H | I | J | K | L | M | N | O
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [9 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisaged Quantity |  |  | Estimated Budget |  | Source of Funds | Prequal ificatio n (Y/N) | Procurem ent Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
1 | Works | 170023410001 | Construction of Okposi Umuoghara (new quarry)- Ebiaji road in Ezza North LGA (12.2km |  | 90000000 |  | 12.2 km |  | 12.2km |  |  | 100000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | March 2022 | Dec.2022
2 | Works | 170023410002 | Construction of Ishiagu Okue-Nzerem Akaeze (11.2km) road in Ivo LGA |  | 30000000 |  | 11.2 km |  | 11.2km |  |  | 10000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | March 2022 | Dec.2022
3 | Works | 170023410003
4 | Works | 170023410004 | Construction of Enyibichiri Ojon Nwida Agricultural road (12.4km) in Ikwo LGA for food production COVID-19 Economic Recovery |  | 117538296.11 | [6 empty] | 20000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | March 2022 | Dec.2022
5 | Works | 170023410005 | Construction of Ukwuachi- Oshiegbe road (11.2km) in Ezza North LGA |  | 100000000 |  | 11.2 km |  | 11.2km |  |  | 50000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | March 2022 | Dec.2022
6 | Works | 170023410006 | Construction of Oferekpe Ovuduechi road (15km) in Izzi LGA (Agricultural farm road) for food production COVID-19 Economic Recovery |  | 206746476.83 |  | 15k m |  | 15km |  |  | 20000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | March 2022 | Dec.2022
7 | Works | 170023410007 | Construction of Abaomege-Ukwu- Ugwlangwu- Okposi Road (25km) in Onicha and Ohaozara LGAs |  | 200000000 |  | 25k m |  | 25km |  |  | 80000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
| A | B | C |  | D | E |  | F |  |  | G |  | H | I | J | K | L | M | N | O
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [9 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  |  | Envisag ed Quantity |  | Estimated Budget |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicatio n Date | Award Date | Project Start Date | Project Completion Date
8 | Works | 170023410008 | Reconstruction of Amasiri-Okposi Uburu Road (23.5km) |  | 973056141.5 |  | 23.5k m |  |  | 23.5km |  | 50000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
9 | Works | 17002341009 | Reconstruction of Ntezie Agba-Isu Road (15km) |  | 786058334.58 |  | 15km |  |  | 15km |  | 800000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
10 | Works | 170023410010 | Reconstruction of Amasiri-Owutu-Oso Edda Road (15km) |  | 150000000 | [6 empty] | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
11 | Works | 170023410011 | Reconstruction of Ezzamgbo-Effium Section of Abakaliki (20km) |  | 800000000 |  | 20km |  |  | 20km |  | 50000000 | I: Budgetary Provision; J: Yes; K: e- procure ment
12 | Works | 170023410012 | Reconstruction of Onunwedu Junction- Elunwovu Roundabout (4.5km) |  | 20000000 |  | 4.5km |  |  | 4.5km |  | 20000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
13 | Works | 170023410013 | Construction of Amakporo-Isu Road (3.5km) |  | 32248472.24 |  | 3.5km |  |  | 4.5km |  | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
14 | Works | 170023410014 | Asphalting of Aabakaliki Township Stadium |  | 30000000 | [6 empty] | 30000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
15 | Works | 170023410015 | Construction of Amenu, Enuegu,Urobo and Umuchima Nweze Road in Uburu (8.5km) |  | 20000000 |  | 8.5km |  |  | 8.5km |  | 50000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022

## Table 2
| A | B | C |  | D | E |  | F |  | G |  | H | I | J | K | L | M | N | O
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [8 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisaged Quantity |  | Estimated Budget |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicatio n Date | Award Date | Project Start Date | Project Completion Date
16 |  | 70023410016 | Construction of Ovudechi- Oyege-Nduofutu Road (3.5km) |  | 30000000 |  | 3.5k m |  | 3.5km |  | 10000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | June 2022 | Dec.2022
17 | Works | 170023410017 | Construction of Eworshade-Nduegu- Amagu Agricultural Road (5km) for food production COVID-19 Economic Recovery |  | 150000000 |  | 5km |  | 5km |  | 0 | I: Budgetary Provision; K: e- procure ment
18 | Works | 170023410018 | Filling and covering of medina and walkway along Enugu-Abakaliki- Expressway |  | 2811281.5 | [5 empty] | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
19 | Works Works | 170023410019 | Construction of Abakaliki Ring Road |  | 43325729.92 | [5 empty] | 20000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
20 | Works | 170023410020 | Dualization of Abakaliki- Afikpo Road |  | 58478900 | [5 empty] | 3000000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
21 | Works | 170023410021 | Dualization of Abakaliki- Enugu Road to Ebonyi State Boundary |  | 0 | [5 empty] | 3000000000 | I: Budgetary Provision; K: e- procure ment; N: Feb.2022; O: Dec.2022
22 | Works | 170023410022 | Construction G.T.C Agba-Elu-Egu-Enu –Isu Agricultural Road (10.3km) COVID-19 Economic Recovery |  | 504201050 |  | 10.3 km |  | 10.3km |  | 30000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
23 | Works | 170023410023 | Construction of Okwuachi Onunweke Nkomoro Road |  | 50000000 | [5 empty] | 5000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022

## Table 3
| A | B | C |  | D | E |  | F |  | G |  | H | I | J | K | L | M | N | O
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [8 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisaged Quantity |  | Estimated Budget |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicati on Date | Award Date | Project Start Date | Project Completion Date
24 | Works | 170023410024 | Dualization of Amasiri – Abakaliki Road junction to Amuro mgbom junction(3.6km) |  | 65122054.02 |  | 3.6km |  | 3.6km |  | 50000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
25 | Works | 170023410025 | Construction of Onueke International roads phase 2 Ezza South LGA (15KM) |  | 20000000 |  | 15km |  | 15km |  | 5000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
26 | Works | 170023410026 | Construction of Ishieke Odomoke road phase 2 (16km) |  | 50000000 |  | 16km |  | 16km |  | 10000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
27 | Works | 170023410027 | Construction of Obuja junction nwanwu market road(9.5km) cov19 Economic recovery |  | 50000000 |  | 9.5km |  | 9.5km |  |  | I: Budgetary Provision; J: Yes; K: e- procurem ent
28 | Works | 170023410028 | Construction of (65km) road in 13 LGAS of the state(5km per LGA) |  | 576996946.82 |  | 5KM per LGA |  | 65km |  | 6,200,000,000.0 0 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
29 | Works | 170023410029 | Construction of Agubia Oronga road |  | 7045000 | [7 empty] | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
30 | Works | 170023410030 | Construction of Uburu Okpanku road to Akeze |  | 0 | [5 empty] | 130000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
31 | Works | 170023410031 | Construction of Okposi internal road |  | 10000000 | [5 empty] | 150000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [8 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisage d Quantity |  | Estimated Budget |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicati on Date | Award Date | Project Start Date | Project Completion Date
32 | Works | 170023410032 | Southern ring road Construction |  | 30000000 | [5 empty] | 10000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
33 | Works | 170023410033 | Construction of Nkaliki – Orizor road (16.7km) |  | 152860317 |  | 16.7k m |  | 16.7km |  | 200,000,000.0 0 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
34 | Works | 170023410034 | Construction Amuzo Amaka road(12km) |  | 100000000 |  | 12km |  | 12km |  | 10000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
35 | Works | 170023410035 | i. Construction of Uburu medical college flyover bridge phase I & II |  | 205405092.75 |  | 65KM | [5 empty] | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
36 | Works | 170023410036 | Construction of Esu Eweze Bridge & 2 no. relief box culvert alongmpu obiozara junction road |  | 100000000 |  | 2 |  | 2 |  | 50000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
37 | Works | 170023410037 | Iv. Construction of Ebunwana ekoli – nguzu road |  | 272926778.05 | [5 empty] | 150,000,000.0 0 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
38 | Works | 170023410038 | v. Construction of roads of zones 5,6,&8 Ochudo Centenary city |  | 486323256.59 | [5 empty] | 150,000,000.0 0 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022
39 | Works | 170023410039 | vi. Construction of New jersey bernner on the Government House peripheral road |  | 95025588.4 | [5 empty] | 5000000 |  | Budgetary Provision | Yes | e- procurem ent |  |  | Feb.2022 | Dec.2022

## Table 4
| A | B | C |  | D | E |  | F |  | G |  |  | H | I | J | K | L | M | N | O
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [9 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisag ed Quantity |  | Estimated Budget |  |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicatio n Date | Award Date | Project Start Date | Project Completion Date
40 | Works | 170023410040 | Construction of a section of Umuoghara Achiegu road (1.6km) |  | 50000000 |  | 1.6km |  | 1.6km |  | 50000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
41 |  | 170023410041 | Construction of 13km Uburu–Akeze road |  | 405203057.95 |  | 13km |  | 13km |  | 400000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
42 | Works | 170023410042 | Construction of Sharon Iboko road (7.3km) |  |  |  | 7.3km |  | 7.3km |  | 50000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
43 | Works | 170023410043 | Construction of drainage facilities along Ukwuachi Oshiegbe Road |  | 20000000 | [5 empty] | 20000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
44 | Works | 170023410044 | Construction of 6 span bridge along Okwue Nzerem-Akaeze-Ishiagu road |  | 100000000 |  | 6span |  | 6 span |  | 50000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
45 | Works | 170023410045 | Dualization of MPU Obiozara road |  | 304548054.6 | [5 empty] | 50000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
46 | Works | 170023410046 | Construction of 3 span bridge at Nkalagu- Ehamufu road to the Government proposed farm |  | 40000000 | [5 empty] | 97578129.54 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
47 | Works | 170023410047 | Construction of 4 span bridge across Esu River along the proposed Uburu-Akaezekwu Road in Ohaozara LGA |  | 70000000 |  | 4span |  | 4 span |  | 20000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [9 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisaged Quantity |  |  | Estimated Budget |  | Source of Funds | Prequ alificat ion (Y/N) | Procure ment Method | Advert Publicatio n Date | Award Date | Project Start Date | Project Completion Date
48 | Works | 170023410048 | Construction of 2 span bridge along Ishieke- Odomeke Road in Ebonyi LGA |  | 50000000 |  | 2span |  | 2span |  |  | 10000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
49 | Works | 170023410049 | Umuchima Enuebor road (6km) |  | 135960490.03 |  | 6km |  | 6km |  |  | 100000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
50 | Works | 170023410050 | Construction of flyover at Amasiri Junction |  | 481020000 | [6 empty] | 500000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
51 | Works | 170023410051 | Construction of flyover bridge at Uburu Onufukuru junction |  | 212977653.6 | [6 empty] | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
52 | Works | 170023410052 | Construction of Iyere flyover bridge in Afikpo South LGA |  | 1,604,348,646.3 6 | [6 empty] | 400000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
53 | Works | 170023410053 | Uburu-Okposi Drains and Median |  | 42474817 | [6 empty] | 50000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
54 | Works | 170023410054 | Dualization of Uburu- Okposi Road |  | 19024377.71 | [6 empty] | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
55 | Works | 170023410055 | Construction Ehimehi River Bridge |  | 0 | [6 empty] | 30000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
56 | Works | 170023410056 | Construction of Uburu- Azaeze Road/Asphalting of Esu Bridge |  | 4322080 | [6 empty] | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [9 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisaged Quantity |  | Estimated Budget |  |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicatio n Date | Award Date | Project Start Date | Project Completion Date
57 | Works | 170023410057 | Construction of 4 span Bridge along Amangu- Uburu Akaeze Road, Asphalting of Esu Bridge |  | 4322080 |  | 4span |  | 4span |  | 0 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
58 | Works | 170023410058 | Concrete pavement for Roundabout/ Island of Medical college flyover |  | 0 | [5 empty] | 50000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
59 | Works | 170023410059 | Game House at Camp David Estate |  | 55040000 | [5 empty] | 200000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
60 | Works | 170023410060 | Game House at Medical College |  | 55040000 | [5 empty] | 200000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
61 | Works | 170023410061 | Construction of Obiozara- Leper colony /Uburu- Obiozara Road |  | 0 | [5 empty] | 100000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
62 | Works | 170023410062 | Construction of Timber Shade flyover Afikpo |  | 150000000 | [5 empty] | 500000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
63 | Works | 170023410063 | Road maintenance |  | 1625000000 | [5 empty] | 1000000000 |  | I: Budgetary Provision; K: e- procure ment; N: Feb.2022; O: Dec.2022
64 | Works | 170023410064 | Abakaliki Internal Road |  | 0 | [5 empty] | 500000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
65 | Works | 170023410065 | Other Roads Interventions in Ebonyi State |  | 0 | [5 empty] | 3000000000 |  |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022

## Table 5
| A | B | C |  | D | E |  | F |  | G |  | H | I | J | K | L | M | N | O
| Procuring Entity Name: |  |  | Ministry of Works and Transport
Procurement Plan for year: 2022
| Date Created: |  |  | 2022-01-31
Comments:
|  |  | Description | [8 empty] | M: Estimated Dates
S/N | Class | UNSPSC (Project Classification) |  |  | COST | Ref No | Unit |  | Envisaged Quantity |  | Estimated Budget |  | Source of Funds | Prequal ificatio n (Y/N) | Procure ment Method | Advert Publicatio n Date | Award Date | Project Start Date | Project Completion Date
66 | Works | 170023410066 | Construction of Bridges |  | 100346437.5 | [5 empty] | 300000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
67 | Works | 170023410067 | Construction of Roundabouts |  | 0 | [5 empty] | 100,,000,000.00 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
68 | Works | 170023410068 | Earthworks on Iyere Edda Flyover Bridge |  | 0 | [5 empty] | 500,,000,000.00 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
69 | Works | 170023410069 | Ancillary concrete works at Iyere flyover |  | 0 | [5 empty] | 200,,000,000.00 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
70 | Works | 170023410070 | Construction of Ameka Road (5km) |  | 0 |  | 5km |  | 5km |  | 200000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
71 | Works | 170023410071 | Construction of Ngbo Road (5km) |  | 0 |  | 5km |  | 5km |  | 200000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
72 | Works | 170023410072 | Amasiri- OwutuEbunwuna-Nguzu Road |  | 0 | [5 empty] | 200000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
73 | Works | 170023410073 | Pilling of Egugwu retaining wall |  | 29305264.56 | [5 empty] | 0 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022
74 | Works | 170023410074 | Construction of Hausa Quarters Flyover, Abakaliki |  | 150000000 | [5 empty] | 500000000 |  | Budgetary Provision | Yes | e- procure ment |  |  | Feb.2022 | Dec.2022