## Sheet1
Procuring Entity and Disposing Entity (MDA) | Ministry of Health
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FIRST QUARTER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Renovation of 8 No.General Hospitals. | 23010122 | Procurement | Works | Direct Procurement (DP) |  | State Budget | State Wide | 200000000 | 200000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 6Months | 24th march 2025 | 26th march 2025 | 12 Months
Procurement of essential equipments for NIGEP Survelliance and Other emergency response to Epidemic Diseases Control | 23010122 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 10000000 | 10000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 6Months
Neglected Tropical Diseases (NTDs) | 23010122 | Procurement | Supplies | Services |  | State Budget | State Wide | 10000000 | 10000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Procurement of HIV Rapid Test Kits, PMTC commodities and HIV/AIDS/ Hepatitis Interventions across the State. | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 40000000 | 40000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 6Months
Provision of medical equipment like testescope for School Health Services | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 6000000 | 6000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 6Months
Procurements of books for Health Education Services | 23010125 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 6000000 | 6000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 6Months
Construction of 1 No. Pharma Grade Central Medical Store at the Centenary City for Drug Distribution. | 23020118 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 300000000 | 300000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Maternal New born and Child Health Week | 23050104 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 60000000 | 60000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 6Months
Construction of 3 major cold store in each senatorial zone of the state, to serve in distributions of both routine and nonroutine drugs | 23020118 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 250000000 | 250000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Procurement of Mama Kits and essential drugs and BEMONC for Reproductive Health services across the State | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 30000000 | 30000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 7th Oct.2025 | 7th Oct.2025 | 8th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Procurement of PPLARC, MVA equipment and cosumables for Family Planning Services at General Hospitals/PHC | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 10000000 | 10000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 7th Oct.2025 | 7th Oct.2025 | 8th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Procurement of 1No of Cold Van for delivery of drugs/Logistics Management Coordinating Unit (LMCU) operational activities | 23010106 - | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | 3rd Sept 2025 | 2nd oct 2025 | 2nd oct 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 14th Oct 2025 | 16h Oct 2025 | 6Months
Production of ANNUAL HUMAN RESOURCE FOR Health FROM THE STATE HEALTH workforce registry for Medical Records | 23050103 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 20000000 | 20000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Production of State Health Account for optimization of health financing | 23050103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000 | 5000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 6Months
Procurement of Office table and chair for the office of the Permanent Secretary | 23010112 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000 | 5000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 6Months
Maternal and Perinatal Death Surveilance and Response (MPDSR) Activities | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 12000000 | 12000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Procurement of 1 Ambulances for Rapid Medical Emergency Response Services | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | 3rd March 2025 | 1st April 2025 | 1st April 2025 |  |  |  | 7th April.2025 | 7th April.2025 | 7th April.2025 | 10th April 2025 | 14th April | 6Months
Nigeria field epidemiology laboratory (NFELT) Programme | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 1000000 | 1000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 6Months
Procurement of office ICT equipment for conduct of Health Operational Research | 23030127 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 2000000 | 2000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 6Months
Procure 2 No. (4 Module) Gene xpert machine for diagnosis of Tuberculosis in the state | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 20000000 | 20000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Equiping of standard Medical Laboratory in the 14 general hospitals | 23030105 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 10000000 | 10000000 | Fixed price contract | 5th Sept 2025 | 6th Oct.2025 | 6th Oct.2025 |  |  |  | 10th oct 2025 | 10th oct 2025 | 10th oct 2025 | 13th oct 2025 | 13th oct 2025 | 6Months
Renovating of drug stores in the 13 LGA across the state | 23030105 - | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 65000000 | 65000000 | Fixed price contract | 1st. Sept 2025 | .30th Sept 2025 | .30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 8th oct 2025 | 8th oct 2025 | 12 Months
Production of Health Manangement Information System Data reporting Tools and other health data reporting tools for the state | 23050103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 50000000 | 50000000 | Fixed price contract | 5th Sept 2025 | 6th Oct.2025 | 6th Oct.2025 |  |  |  | 10th oct 2025 | 10th oct 2025 | 10th oct 2025 | 13th oct 2025 | 13th oct 2025 | 6Months
Rehabilitation of Infrastructure of Ebonyi State teaching Hospital | 23020118 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 35000000 | 35000000 | Fixed price contract | 5th Sept 2025 | 6th Oct.2025 | 6th Oct.2025 |  |  |  | 10th oct 2025 | 10th oct 2025 | 10th oct 2025 | 13th oct 2025 | 13th oct 2025 | 12 Months
Construction of 6 No. 2 Bedroom flats for health workers accommodation in the 14 General Hospitals | 23020104 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 1600000000 | 1600000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of 3Nos. Newborn Centers in the State | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 50000000 | 50000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Implementation of Decisions of National Council on Health programme | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000 | 5000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Construction of Ebonyi State Ultra-Model Diagnostic Center | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 2500000000 | 2500000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Free Mobile Clinic/ Health Awareness Campaign | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5200000 | 5200000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Procurement of hospital Machines/Equipment | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 20000000 | 20000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 6Months
Iprocurement of boxes for food distribution programmes to provide nutritional meals and supplements to school children and other vulnerable population. | 23050101 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 50000000 | 50000000 | Fixed price contract | 3rd March 2025 | 1st April 2025 | 1st April 2025 |  |  |  | 7th April.2025 | 7th April.2025 | 7th April.2025 | 10th April 2025 | 14th April | 6Months
Monitoring and Evaluation and Qulity Assurance Assessment | 23050103 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000 | 5000000 | Fixed price contract | 3rd March 2025 | 1st April 2025 | 1st April 2025 |  |  |  | 7th April.2025 | 7th April.2025 | 7th April.2025 | 10th April 2025 | 14th April | 6Months
Procurement of equipment for nursing care promotion and advancement | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 20000000 | 20000000 | Fixed price contract | 3rd March 2025 | 1st April 2025 | 1st April 2025 |  |  |  | 7th April.2025 | 7th April.2025 | 7th April.2025 | 10th April 2025 | 14th April | 6Months
Procurement of cancer screening equipment/kits for cancer screening across the 13 LGAs (Mobile) | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | 5th Aug 2025 | 3rd Sept. 2025 | 3rd Sept. 2025 |  |  |  | 9th Sept.2025 | 9th Sept.2025 | 9th Sept.2025 | 12th Sept 2025 | 15th Sept 2025 | 6Months
Establishment/equiping of Care of the Elderly unit in all the 14 General Hospitals in the State. | 23010122 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 6000000 | 6000000 | Fixed price contract | 5th Aug 2025 | 3rd Sept. 2025 | 3rd Sept. 2025 |  |  |  | 9th Sept.2025 | 9th Sept.2025 | 9th Sept.2025 | 12th Sept 2025 | 15th Sept 2025 | 6Months
Procurement of office equipment for mental health units office | 23010112 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 1000000 | 1000000 | Fixed price contract | 5th Aug 2025 | 3rd Sept. 2025 | 3rd Sept. 2025 |  |  |  | 9th Sept.2025 | 9th Sept.2025 | 9th Sept.2025 | 12th Sept 2025 | 15th Sept 2025 | 6Months
Construction of 1No Health Clinic for Abakaliki Mechanic Site and Abakaliki Rice Mill (CCD Project) | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 200000000 | 200000000 | Fixed price contract | 5th Aug 2025 | 3rd Sept. 2025 | 3rd Sept. 2025 |  |  |  | 9th Sept.2025 | 9th Sept.2025 | 9th Sept.2025 | 12th Sept 2025 | 15th Sept 2025 | 6Months
Construction of burn and bury pit at MDG Ededeagu facility in Ebonyi LGA (CCD Project) | 23020118 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | 5th Aug 2025 | 3rd Sept. 2025 | 3rd Sept. 2025 |  |  |  | 9th Sept.2025 | 9th Sept.2025 | 9th Sept.2025 | 12th Sept 2025 | 15th Sept 2025 | 12 Months
Installation of alternative power source (Solar Power) in the 14 General Hospitals | 23020103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 1000000000 | 1000000000 | Fixed price contract | 6th Oct.2025 | 4th Nov.2025 | 4th Nov.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 13th Nov 2025 | 17th Nov 2025 | 12 Months
Contruction and solarization of 1No cold room | 23020118 - | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 250000000 | 250000000 | Fixed price contract | 2nd Oct.2025 | 30th Oct.2025 | 30th Oct.2025 |  |  |  | 3rd Nov. 2025 | 3rd Nov. 2025 | 3rd Nov. 2025 | 10th Nov 2025 | 14th Nov 2025 | 12 Months
Contruction of 3Nos. CMS in the 3 geopolitical zones in the State. | 23020118 - | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 150000000 | 150000000 | Fixed price contract | 6th Oct.2025 | 4th Nov.2025 | 4th Nov.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 13th Nov 2025 | 17th Nov 2025 | 12 Months
Procurement of 3No delivery van for distribution of drugs across the 13 LGAs | 23010106 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 150000000 | 150000000 | Fixed price contract | 6th Oct.2025 | 4th Nov.2025 | 4th Nov.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 13th Nov 2025 | 17th Nov 2025 | 6Months
Construction of 1No Health Clinic at Abakaliki International Market | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 150000000 | 150000000 | Fixed price contract | 6th Oct.2025 | 4th Nov.2025 | 4th Nov.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 13th Nov 2025 | 17th Nov 2025 | 12 Months
Procurement of 2No Projector and Projector Screen | 23010139 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 800000 | 800000 | Fixed price contract | 6th Oct.2025 | 4th Nov.2025 | 4th Nov.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 13th Nov 2025 | 17th Nov 2025 | 6Months
Establishment/Equiping of DPRS-HMIS Office for Integrated Supportive Supervission system of Ebonyi Health System | 23020101 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 30000000 | 30000000 | Fixed price contract | 3rd Nov. 2025 | 2nd Dec. 2025 | 2nd Dec. 2025 |  |  |  | 8th Dec 2025 | 8th Dec 2025 | 8th Dec 2025 | 15th Dec 2025 | 16th Dec 2025 | 6Months
Equiping of 6No. 2 Bedroom flat in each General Hospital in the State | 23020104 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 1000000000 | 1000000000 | Fixed price contract | 3rd Nov. 2025 | 2nd Dec. 2025 | 2nd Dec. 2025 |  |  |  | 8th Dec 2025 | 8th Dec 2025 | 8th Dec 2025 | 15th Dec 2025 | 16th Dec 2025 | 6Months
Establishment and construction of Hepatiatse Centre in the State | 23020106 - | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 200000000 | 200000000 | Fixed price contract | 3rd Nov. 2025 | 2nd Dec. 2025 | 2nd Dec. 2025 |  |  |  | 8th Dec 2025 | 8th Dec 2025 | 8th Dec 2025 | 15th Dec 2025 | 16th Dec 2025 | 6Months
Establishment and construction of Pharmacutical drugs manufacturing company at Offerekpe Agbaja in Izzi LGA | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 4000000000 | 4000000000 | Fixed price contract | 3rd Nov. 2025 | 3rd Dec. 2025 | 3rd Dec. 2025 |  |  |  | 8th Dec 2025 | 8th Dec 2025 | 8th Dec 2025 | 15th Dec 2025 | 16th Dec 2025 | 6Months
Construction of 3 Nos Incinerator system in 3 GHs at the 3 senatorial zones for disposal of medical waste in the state | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 300000000 | 300000000 | Fixed price contract | 1st july 2025 | 30th july 2025 | 30th july 2025 |  |  |  | 4th AUG .2025 | 4th AUG .2025 | 4th AUG .2025 | 7TH Aug 2025 | 11th Aug 2025 | 12 Months
Procurement of multi purpose (Printer, Photocopier, scanner) for the office of DPRS | 23010114 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000 | 5000000 | Fixed price contract | 1st may. 2025 | 30th may 2025 | 30th may 2025 |  |  |  | 5th June 2025 | 5th June 2025 | 6th June 2025 | 9th June 2025 | 11th June 2025 | 6Months
Procurement of 1No Sound proof generator for State Ministry of Health | 23010119 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000 | 5000000 | Fixed price contract | 1st April 2025 | 30th April 2025 | 30th April 2025 |  |  |  | 5th may .2025 | 5th may .2025 | 7th May 2025. | 9th May 2025 | 12th May 2025 | 6Months
Development and production of SMoH Annual Operational Plan | 23050101 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | 1st April 2025 | 30th April 2025 | 30th April 2025 |  |  |  | 5th may .2025 | 5th may .2025 | 7th May 2025. | 9th May 2025 | 12th May 2025 | 6Months
Development and production of SMoH MTSS | 23050101 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | [11 empty] | 6Months
Production of manuals for Conducting monthly data validation meetings | 23050101 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 130000000 | 130000000 | Fixed price contract | 10th feb 2025 | .11th March 2025 | .11th March 2025 |  |  |  | 17th March.2025 | 17th March.2025 | 17th March.2025 | 19th march 2025 | 21st march 2025 | 6Months
Conduct quarterly Data Quality Accessment (DQA) | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 100000000 | 100000000 | Fixed price contract | 1st April 2025 | 30th April 2025 | 30th April 2025 |  |  |  | 7thth may .2025 | 8th may .2025 | 8th May 2025. | 12th May 2025 | 15th May 2025 | 6Months
Installation and equiping of 15 Gen. Hospitals in the 13 LGAs | 23010122 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 10000000 | 10000000 | Fixed price contract | 2nd April 2025 | 1st may 2025 | 1st may 2025 |  |  |  | 7th may .2025 | 7th may .2025 | 7th May 2025. | 9th May 2025 | 12th May 2025 | 6Months
Procurement of 15Nos Generator Sets for the 15 Gen. Hospitals in the State | 23010119 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 10000000 | 10000000 | Fixed price contract | 10th feb 2025 | .11th March 2025 | .11th March 2025 |  |  |  | 17th March.2025 | 17th March.2025 | 18th March.2025 | 19th march 2025 | 24th march 2025 | 6Months
Construction of 3No. New Specialist Hospital in the 3 senatorial zones | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 5000000000 | 5000000000 | Fixed price contract | 1st April 2025 | 30th April 2025 | 30th April 2025 |  |  |  | 5th may .2025 | 5th may .2025 | 7th May 2025. | 9th May 2025 | 12th May 2025 | 12 Months
Production of Ready to Use Therapeutic Food (RUTF) and Micro-Nutrient, MMS and other Nutrition services | 23010122 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 220000000 | 220000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Maternal and child health programmes for malnourished children in the State | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 200000000 | 200000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Procurement of food processing equipment for the Nutrition Department to combat acute malnutrition in the State | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 80000000 | 80000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Rehabilitation of the centre for the Management of Lassa fever cases in the State | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 300000000 | 300000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 12 Months
Establishment of Blood Bank centre in the 3 senatorial zone of the Sate | 23020106 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 300000000 | 300000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Management of Oxygen supply to the State Health facilities | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 80000000 | 80000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Conduct of integrated management of Childhood illnesses (1mci) | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 200000000 | 200000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Capacity building for the conduct of 2025 Joint Health Annual Review of the State | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 50000000 | 50000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Capacity building for the development of the Ministry of Health Annual Operational Plan | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 20000000 | 20000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 6Months
Production of Ebonyi State Health Workforce Registry | 23010122 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 50000000 | 50000000 | Fixed price contract | 6th Oct.2025 | 4th Nov 2025 | 4th Oct.2025 |  |  |  | 10th Nov. 2025 | 10th Nov. 2025 | 10th Nov. 2025 | 12th Nov 2025 | 13th Nov 2025 | 12 Months