## Sheet1
Procuring Entity and Disposing Entity (MDA) | Ministry of Infrastructural Development and Concession
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FISRT QUARTER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Construction of 280km Road in 140 Communities of Ebonyi State 2KM per community (CCD) | 23020114 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 11000000000 | 11000000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of 13.480km OriuozorOnueke Road | 23020114 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | EZZA SOUTH | 3000000000 | 3000000000 | Fixed price contract | 1st July 2-025 | 30th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
Construction of 3.8km Hon. Ugo Chima Road Ezza South | 23020114 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | EZZA SOUTH | 300000000 | 300000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of 3 span bridge at Akadoro river, Alubeleke Ezza North LGA | 23020116 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | EZZA NORTH | 500000000 | 500000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of Ameke-Ike river road, Ishiagu, Ivo LGA (4km) | 23020114 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | IVO | 800000000 | 800000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of 3 span bridge along EkkaInyere road, Akadoro river, Ezza North LGA | 23020116 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | EZZA NORTH LGA | 550000000 | 550000000 | Fixed price contract | 4th feb.. 2025 | 5th march 2025 | 5th March. 2025 |  |  |  | 10th March.2025 | 10th March.2025 | 10th March.2025 | 17th march 2825 | 19th march 2825 | 12 Months
Construction of 3-span Reinforced concrete Bridge and 2no. 3mX3m cell culverts, Afikpo North Local Government Area | 23020116 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | AFIKPO NORTH | 700000000 | 700000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of 3-span bridges 2no Box culverts at Ike River, Amaeke Ishiagu | 23020116 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | IVO | 600000000 | 600000000 | Fixed price contract | 1st July 2-025 | 30th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
Construction of Ekwetekwe-OgbuinyaguUmuezeoka Road (4km) in Ezza North LGA | 23020114 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | EZZA NORTH | 750000000 | 750000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of 2 span Abe bidge along Iziogo road | 23020116 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | IZZI LGA | 800000000 | 800000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months