## Sheet1
Procurement Plan for | OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT
Procuring Entity and Disposing Entity (MDA) | OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT
Procuring Entity and Disposing Entity (LGAs) | EBONYI STATE
Procurement Plan for financial year | 2025
Date Last Updated | FIRST QUARTER 2025
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Awarding Authority | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Purchase of 3 Nos HP Desktop (2) for Office of SSG and (1) for Perm. Sec. | 23010113- | Procurement | Supplies | Direct Procurement (DP) |  | State Budget | Abakaliki | BPP | 1200000 | 1200000 | Fixed price contract | 12TH Feb 2025 | 13TH March 2025 | 13TH March 2025 |  |  |  | 19th March 2025 | 19th March 2025 | 19th March 2025 |  |  | 2 Months
Purchase of Vehicles for Government Officers | 23010105 - | Procurement | Supplies | Selective International Bidding (SIB) |  | State Budget | Abakaliki | BPP | 5000000000 | 5000000000 | Fixed price contract | 21st Jan 2025 | 19th Feb 2025 | 19th Feb 2025 |  |  |  | 24th Feb 2025 | 24th Feb 2025 | 24th Feb 2025 |  |  | 12 Months
Rehabilitation of the Lagos State EBSG property | 23030103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Lagos | BPP | 2000000 | 2000000 | Fixed price contract | 24th Feb 2025 | 25th March 2025 | 25th March 2025 |  |  |  | 2nd April 2025 | 2nd April 2025 | 2nd April 2025 |  |  | 2 Months
Purchase of 2 multipurpose Printers | 23010114 | Procurement | Supplies | Direct Procurement (DP) |  | State Budget | Abakaliki | BPP | 800000 | 800000 | Fixed price contract | 7th April 2025 | 8th May 2025 | 8th May 2025 |  |  |  | 15th May 2025 | 15th May 2025 | 15th May 2025 |  |  | 2 Months
Consultancy on Capital Project of Ebonyi State Assets and inventory control management | 23050101 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | BPP | 15000000 | 15000000 | Fixed price contract | 6th May 2025 | 5th June 2025 | 5th June 2025 |  |  |  | 11th June 2025 | 12th June 2025 | 13th June 2025 | 16th June 2025 | 16th June 2025 | 1 Month
Renovation of Cabinet Office (curtains and its accessories for all the departments | 23030121 | Procurement | Supplies | Direct Procurement (DP) |  | State Budget | Abakaliki | BPP | 3000000 | 3000000 | Fixed price contract | 10th Feb.2025 | 11th March 2025 | 11th March 2025 |  |  |  | 17th March 2025 | 17th March 2025 | 18th march 2025 | 24th March 2025 | 26th March 2025 | 3 Months
Purchase of Office furniture and fittings | 23010112 | Procurement | Supplies | Direct Procurement (DP) |  | State Budget | Abakaliki | BPP | 10000000 | 10000000 | Fixed price contract | 4th Sept. 2025 | 3rd Oct. 2025 | 3rd Oct. 2025 |  |  |  | 9th Oct. 2025 | 9th Oct. 2025 | 9th Oct. 2025 | 14th Oct.2025 | 16th Oct 2025 | 2 Months
Purchase of 1 No Photocopying machine (Resographic) | 23010115 | Procurement | Supplies | Direct Procurement (DP) |  | State Budget | Abakaliki | BPP | 10000000 | 10000000 | Fixed price contract | 6th Jan.2025 | 5th Feb .. 2025 | 5th Feb.2025 |  |  |  | 11th Feb..2025 | 11th Feb..2025 | 11th Feb..2025 | Feb.2025 | Feb.2025 | 1 Month
Lagos State Government Land Use charge on EBSG property | 23010101 | Procurement | Supplies | Direct Method (DM) | 1 | State Budget | Lagos | BPP | 2000000 | 2000000 | Fixed price contract | 6th Jan.2025 | 5th Feb .. 2025 | 5th Feb.2025 |  |  |  | 11th Feb..2025 | 11th Feb..2025 | 11th Feb..2025 | Feb.2025 | Feb.2025 | 1 Month
Construction of Housing Unit to EXCO Members | 23010101 | Procurement | Works | Disposal by Public Bidding (DPB) |  | State Budget | Abakaliki | BPP | 1000000000 | 1000000000 | Fixed price contract | 6th Jan.2025 | 5th Feb .. 2025 | 5th Feb.2025 |  |  |  | 11th Feb..2025 | 11th Feb..2025 | 11th Feb..2025 | Feb.2025 | Feb.2025 | 24 Months