## Sheet2
Procuring Entity and Disposing Entity (MDA) | Ministry of Primary and Secondary Education
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FISRT QUARTER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Production of 5000 school census booklet and conduct of school census exercise for 2024/2025. | 23050101 | Procurement | Supplies | Shortlisting With Publication Of Expression Of Interest (SLP) |  | State Budget | 41110100 - ABAKALIKI | 30000000 | 30000000 | Fixed price contract | 12TH Feb 2025 | 13TH March 2025 | 13TH March 2025 |  |  |  | 19th March 2025 | 19th March 2025 | 19th March 2025 | 24th March 2025 | 31st march 2025 | 12 Months
Purchase of essential teaching/learning materials (diaries, Attendance registers etc. for senior Sec. Schools, including Amagu Onicha primary School, Ameka Primary School, Cps Mgbom etc. (CCD) |  | Procurement | Supplies | Shortlisting With Publication Of Expression Of Interest (SLP) |  | State Budget | 41110100 - ABAKALIKI | 200000000 | 200000000 | Fixed price contract | 21st Jan 2025 | 19th Feb 2025 | 19th Feb 2025 |  |  |  | 24th Feb 2025 | 24th Feb 2025 | 24th Feb 2025 | 28th February 2025 | 6th March 2025 | 6 Months
Equipping Of Early Child Care Dev. Edu Centres In The State’s Pri. Schools (10 per Zone) | 23010124 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | 41141400 - State Wide | 200000000 | 200000000 | Fixed price contract | 24th Feb 2025 | 23rd March 2025 | 23rd March 2025 |  |  |  | 2nd April 2025 | 2nd April 2025 | 2nd April 2025
Rehabilitation of 60 NO.Public Dilapidated School Buildings 20 per Zone (CCD) | 23010139 | Procurement | Works | Shortlisting With Publication Of Expression Of Interest (SLP) |  | State Budget |  | 800000000 | 800000000 | Fixed price contract | 7th April 2025 | 8th May 2025 | 8th May 2025 |  |  |  | 15th May 2025 | 15th May 2025 | 15th May 2025 | 21st May 2025 | 27th May 2025 | 6 Months
Procurement Of 35 No Subjects Curriculum For Public Primary And Public Secondary Schools In The State. |  | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 6138200 | 6138200 | Fixed price contract | 6th May 2025 | 5th June 2025 | 5th June 2025 |  |  |  | 11th June 2025 | 12th June 2025 | 13th June 2025 | 16th June 2025 | 16th June 2025
Procurement Of 2 No. Braille embossers for translating soft copy or print into braille | 23010124 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 6138200 | 6138200 | Fixed price contract | [9 empty] | 24th March 2025 | 26th March 2025 | 1 Months
Procurement Of 60 No. Braille Boards With Stylus For Special Schools | 23010124 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 1572000 | 1572000 | Fixed price contract | [9 empty] | 14th Oct.2025 | 16th Oct 2025 | 2 Months
Provision Of 60 Units Of Talking Calculators | 23010124 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 628800 | 628800 | Fixed price contract | [9 empty] | Aug.2025 | Aug.2025 | 1 Months
Procurement of 60 Braille Mathematical Sets | 23010124 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 1179000 | 1179000 | Fixed price contract | [9 empty] | Feb.2025 | Feb.2025 | 1 Month
Procurement Of 100 Reams Of Braille Paper | 23010124 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 786000 | 786000 | Fixed price contract | [9 empty] | Feb.2025 | Feb.2025 | 1 Month
Provision Of 60 Pieces Of Tape Recorders | 23010139 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 1572000 | 1572000 | Fixed price contract | [9 empty] | 8th Sept. 2025 | 15th Sept.2025 | 1 Month
Provision Of 60 Pieces Of Typewriting Machines | 23010116 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 2358000 | 2358000 | Fixed price contract | [9 empty] | Oct.2025 | Oct.2025 | 1 Month
Provision Of 4 Nos. Photocopying Machines for Special Schools | 23010115 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 6000000 | 6000000 | Fixed price contract | [9 empty] | 2nd April 2025 | 2025-05-01 | 1 Month
Provision Of 6 Nos. Printers for Special Schools | 23010114 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 786000 | 786000 | Fixed price contract | [9 empty] | 2025-07-01 | 2025-07-01 | 1 Month
Provision of 6 Nos. Scanners for Special Schools | 23010118 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 900000 | 900000 | Fixed price contract | [9 empty] | 16th June 2025 | 25th June 2025 | 1 Month
Food and Nutrition: Engagement Of Youths And Women In Agriculture | 23050101 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 20000000 | 20000000 | Fixed price contract | 11th March 2025 | 9th April 2025 | 9th April 2025 |  |  | 17th March 2025 | 17th March 2025 | 18th march 2025 | 24th March 2025 | 26th March 2025 | 31st March 2025 | 6Months
Procurement of 4 No. Braille Embossers (for translating Soft Copy or Print into Braille) for State Special School for the Blind,Izzi & Dr. Uche Azikiwe Special Education Centre,Okposi, Ohaozara LGA | 23010124 | Procurement | Works | Shortlisting With Publication Of Expression Of Interest (SLP) |  | State Budget | 41110100 - ABAKALIKI | 40000000 | 40000000 | Fixed price contract | 19th Feb 2025 | 20th March 2025 | 20th March 2025 |  |  | 24th Feb 2025 | 24th Feb 2025 | 24th Feb 2025 | 14th March 2025 | 14th March 2025 | 24th Mrch 2025 | 6 Months
Procurement Of Textbooks And Reference Materials |  |  |  |  | 23010124 | State Budget |  | 13100000 |  | Fixed price contract | 5th Feb .. 2025 | 5th Feb.2025 |  |  |  | 11th Feb..2025 | 11th Feb..2025 | 11th Feb..2025 | Feb.2025 | Feb.2025 | 1 Month
Completion of 39 No. 22-Classroom blocks(3per LGA) | 23020107 | Procurement | Works | Direct Method (DM) |  | State Budget | 41110100 - ABAKALIKI | 3000000000 | 3000000000 | Fixed price contract | 5th Jan 2025 | 7th Feb .. 2025 | 7th Feb .. 2025 |  |  |  | 14th Feb..2025 | 14th Feb..2025 | 17th Feb..2025 | Feb.2025 | Feb.2025 | 6 Months
Capacity Development of Teachers and Education Managers | 23050101 | Procurement | Consulting Services | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 250000000 | 250000000 | Fixed price contract | 5th June 2025 | 4th July 2025 | 4th July 2025 |  |  | 11th June 2025 | 12th June 2025 | 13th June 2025 | 16th June 2025 | 16th June 2025 | 2025-07-01 | 6 Months
Monitoring and Evaluation Of Education Policies ,Programmes,Projects, And Quality Assurance Assessment | 23050103 | Procurement | Non Consultancy Services | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 26200000 | 26200000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Furnishing/provision of desks ,chairs, Administrative tables, lab equipment etc. for 39 No. 22 classroom buildings |  | Procurement | Disposals | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 200000000 | 200000000 | Fixed price contract | 3rd March 2025 | 1st April 2025 | 1st April 2025 |  |  |  | 10th April 2025 | 10th April 2025 | 15th April 2025 | 15th April 2025 | 28th Apeil 2025 | 12 Months