## Sheet1
| EBONYI STATE | GOVERNMENT
| Procurement Plan for | Office of the Deputy Governor
Procuring Entity and Disposing Entity (MDA) | Office of the Deputy Governor
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FISRT QUARTER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Rehabilitation of Office Building of the Deputy Governor Anne | 23030121 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 10000000 | 10000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Purchase of 1 No. Hilux Pick Up Van for State Boundary Committee | 23010106 | Procurement | Supplies | Open Domestic Bidding (ODB) | 1 | State Budget | 41110100 - ABAKALIKI | 10000000 | 10000000 | Fixed price contract | 1st July 2025 | 30th July 2025 | 30th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 6Months
Purchase of 1 No. 18 seaters Bus for Deputy Governor's Office | 23010108 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 2000000 | 2000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
urchase of Leather Upholstery Chairs and Executive table for the Deputy Governor's Office | 23010112 | Procurement | Works | Direct Method (DM) |  | State Budget | 41110100 - ABAKALIKI | 1500000 | 1500000 | Fixed price contract | 5th Sept 2025 | 6th Oct.2025 | 6th Oct.2025 |  |  |  | 3rd Nov. 2025 | 3rd Nov. 2025 | 3rd Nov. 2025 |  |  | 6Months
Purchase of Sporting/Games Equipment; Complete set of Gym Equipment, for Lodge: 1 No. Tread Mill, 1 No. Upright Bike, 1 No. Smith Machine, 1 No. Recumbent Stepper, etc | 23010126 | Procurement | Supplies | Open Domestic Bidding (ODB) | 1 | State Budget | 41110100 - ABAKALIKI | 2000000 | 2000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Purchase of Office Equipment:- Upholsery Set for Deputy Chief of Staff | 23010112 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 2000000 | 2000000 | Fixed price contract | 4th feb.. 2025 | 5th march 2025 | 5th March. 2025 |  |  |  | 10th March.2025 | 10th March.2025 | 10th March.2025 | 17th march 2825 | 19th march 2825 | 12 Months
Purchase of 4 No. Medium size Refidgerator for Office of the Deputy Chief of Staff, Admin, Finance and PRS Department of the Office of the Deputy Governror | 23010112 | Procurement | Supplies | Direct Procurement (DP) | 4 | State Budget | 41110100 - ABAKALIKI | 2000000 | 2000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Purchase/Installation of CCTV for Security Surveilance in the Office of the Deputy Governor | 2301012 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 2000000 | 2000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
Purchase and installation of Internet Infrastructure in the Deputy Governor's Office/Boundary Secretariat | 23050102 | Procurement | Works | Quotations (QUOT) |  | State Budget | 41110100 - ABAKALIKI | 1000000 | 1000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Purchase of 4 No Desktop Computers for Perm Sec Office, Admin, PRS, Accounts Departments | 23010113 | Procurement | Works | Open Domestic Bidding (ODB) | 4 | State Budget | 41110100 - ABAKALIKI | 500000 | 500000 | Fixed price contract |  | 6th Jan 2025 | 4th Feb 2025 | 4th Feb 2025 |  |  | 10th Feb 2025 | 10th Feb 2025 | 10th Feb 2025 |  |  | 12 Months
Purcahse of 1 No. Photocopying Machine for PRS Department | 23010115 | Procurement | Works | Open Domestic Bidding (ODB) | 1 | State Budget | 41110100 - ABAKALIKI | 750000 | 750000 | Fixed price contract | [6 empty] | 10th Feb 2025 | 10th Feb 2025 | 11th Feb 2025 | 13th Feb 2025 | 14th Jan 2025 | 3Months
Inter-State Boundary Committee (Mapping) | 23020122 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 10000000 | 10000000 | Fixed price contract | [9 empty] | 1st Aug.2025 | 7th Aug. 2025 | 6 Months
Purchase of 3 No. Steel Cabinet for Admin, Finance and PRS departments of the Office of the Deputy Governor | 23010112 | Procurement | Supplies | Shopping Method (SM) | 3 | State Budget | 41110100 - ABAKALIKI | 900000 | 900000 | Fixed price contract | [9 empty] | 20th May 2025 | 26th May 2025 | 3 Months