## Sheet1
EBONYI STATE | GOVERNMENT
Procurement Plan for | Ebonyi State Road Maintenance Agency (EBROMA)
Procuring Entity and Disposing Entity (MDA) | Ebonyi State Road Maintenance Agency (EBROMA)
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | First quarter
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Rehabilitation of Federal Roads within Abakaliki | 23030113 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 400000000 | 400000000 | Fixed price contract | 12TH Feb 2025 | 13TH March 2025 | 13TH March 2025 |  |  |  | 19th March 2025 | 19th March 2025 | 19th March 2025 | 20th March 2025 | 26th March 2025 | 12 Months
Rehabilitation of State Roads in the capital city | 23030113 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | 41110100 - ABAKALIKI | 500000000 | 500000000 | Fixed price contract | 21st Jan 2025 | 19th Feb 2025 | 19th Feb 2025 |  |  |  | 24th Feb 2025 | 24th Feb 2025 | 24th Feb 2025 | 25th Feb. 2025 | 27th Feb 2025 | 12 Months
Purchase of 2 Nos. Asphalt/ Concrete cutting machine @ 750,000 each | 23010139 | Supplies | Supplies | Open Domestic Bidding (ODB) | 2 | State Budget | 41110100 - ABAKALIKI | 1500000 | 1500000 | Fixed price contract | [9 empty] | 24th March 2025 | 2nd April 2025 | 1Month
Purchase of 10nos. Of Jack hammer machines @ N350,000.00 |  | Procurement | Supplies | Open Domestic Bidding (ODB) | 10 | State Budget | 41110100 - ABAKALIKI | 3500000 | 3500000 | Fixed price contract | [10 empty] | 15th May 2025 | 1Month
Purchase of 6 Nos. Poker/ concrete vibrator machine @ N300,000.00 each | 23010139 | Procurement | Supplies | Open Domestic Bidding (ODB) | 6 | State Budget | 41110100 - ABAKALIKI | 1800000 | 1800000 | Fixed price contract | [9 empty] | Feb.2025 | Feb.2025 | 1Month
Purchase of 2Nos. 1m3 Concrete mixer @ 3,000,000 | 23010139 | Procurement | Supplies | Open Domestic Bidding (ODB) | 2 | State Budget | 41110100 - ABAKALIKI | 6000000 | 6000000 | Fixed price contract | [10 empty] | 26th March 2025 | 1Month